StreamGuard

Phase 3 — Preprocessing Pipeline

Complete 7-Stage Implementation Guide

Stories P3-S1 through P3-S7 with Claude Code Prompts

Production Issues Review Included

| Phase 3 of 7 | Stages 7 total | Duration 7–14 days | Output train/val/test.h5 |
| --- | --- | --- | --- |

March 2026  |  StreamGuard v1.0  |  Implementation-Ready

# 1. Phase 3 Overview

Phase 3 transforms raw collected JSONL samples from Phase 2 into the final train/val/test HDF5 graph tensors that the StreamGuard model (Phase 4) trains on. It is the most time-consuming phase in the project — Joern CPG construction alone takes 3–4 days for 40K samples. Start preprocessing as early as possible, even before Phase 2 collection is fully complete (SARD + ExploitDB give sufficient data to begin).

✔ TIP / NOTE Start Phase 3 on Day 3 using SARD + ExploitDB data. Do NOT wait for all API collectors to finish. Stages 1–2 run immediately on SARD data. Merge additional sources as they complete.

## 1.1 Pipeline Flow

| Stage | Script | Input | Output | Runtime (40K) |
| --- | --- | --- | --- | --- |
| 1: Clean | stage1_clean.py | raw/*.jsonl | cleaned/samples.jsonl | 2–4 hours |
| 2: Dedup | stage2_dedup.py | cleaned/ | deduped/samples.jsonl | 1–2 hours |
| 3: CFA Gen | stage3_cfa.py | deduped/ (vuln only) | with_cfa/samples.jsonl | 22+ hours (API) |
| 4: CPG Build | stage4_cpg.py | with_cfa/ | cpg/*.json | 3–4 days (Joern) |
| 5: Embed | stage5_embed.py | cpg/ | embedded/*.npz | 4–8 hours (GPU) |
| 6: Graphs | stage6_graphs.py | embedded/ | graphs/all_graphs.h5 | 1 hour |
| 7: Split | stage7_split.py | graphs/all_graphs.h5 | final/{train,val,test}.h5 | 10 min |

⛔ CRITICAL ABSOLUTE RULE: Run stages in order. Stage N reads from Stage N-1 output. Never skip stages. Never run Stage 5 before Stage 4 is fully complete. Each stage has a --dry-run flag — always test with 20 samples before full runs.

## 1.2 Pre-Requisites from Phase 2

| Pre-Requisite | Source | Why It Matters |
| --- | --- | --- |
| data/raw/merged/all_samples.jsonl (30K+) | Phase 2 P2-S7 audit | Main input — must pass all 10 audit checks |
| schema.py + validate_sample() | Phase 2 P2-S1 | Stage 1 validation uses this — wrong schema = silent data loss |
| ANTHROPIC_API_KEY in .env | New for Phase 3 | Stage 3 CFA generation calls Claude Haiku |
| JOERN_BIN + JOERN_EXPORT in .env | New for Phase 3 | Stage 4 CPG construction — must be Joern 4.x |
| gcc available on PATH | System dependency | Stage 3 CFA validation gate |
| GPU available (Colab or local) | New for Phase 3 | Stage 5 CodeBERT node embedding — CPU takes 87 hours |
| datasketch, h5py, transformers installed | requirements.txt | Stage 2 (MinHash), Stage 5 (CodeBERT), Stage 6 (HDF5) |
| At least 20 GB free disk space | Infrastructure | CPG files + embeddings + HDF5 = ~10 GB total |

## 1.3 Story Map

| Story | Stage(s) | Day | Priority | Gate to Next |
| --- | --- | --- | --- | --- |
| P3-S1 | Stage 1: Clean & Normalize | Day 1 | P0 | All samples normalized, #ifdef stripped |
| P3-S2 | Stage 2: Deduplicate | Day 1 | P0 | 4-level dedup complete, pair_id integrity verified |
| P3-S3 | Stage 3: CFA Generation | Day 2–3 | P0 | Compile rate >= 80%, pattern removal >= 60% |
| P3-S4 | Stage 4: CPG Construction | Day 3–7 | P0 | DFG edges > 0, taint coverage >= 20%, 0 broken pairs |
| P3-S5 | Stage 5: Node Embedding | Day 7–8 (GPU) | P0 | All .npz files created, shape (N, 824), no NaN |
| P3-S6 | Stage 6: Graph Tensors | Day 8 | P0 | all_graphs.h5 validated, edge_index bounds OK |
| P3-S7 | Stage 7: Split + Audit | Day 9 | P0 | pre_training_audit.py: all 9 checks PASS |

# 2. Story P3-S1 — Stage 1: Clean & Normalize

| Item | Detail |
| --- | --- |
| File to build | training/scripts/preprocessing/stage1_clean.py |
| Test file | tests/test_story_p3s1.py |
| Input | data/raw/merged/all_samples.jsonl (or per-source JSONL files) |
| Output | training/data/processed/cleaned/samples.jsonl |
| Duration | 2–4 hours for 40K samples |
| Depends on | Phase 2 P2-S7 audit PASS |

## 2.1 What It Does

Stage 1 normalizes all raw C function code into a clean, consistent format ready for deduplication. It handles SARD-specific #ifdef stripping, validates function boundaries with tree-sitter, removes comments, and enforces length filters.

### Operations (in order per sample)

| Step | Operation | Detail |
| --- | --- | --- |
| 1 | Encoding fix | chardet detection; re-encode as UTF-8. Handle latin-1 fallback. |
| 2a | Preprocessor strip (SARD only) | Remove #ifdef/#ifndef/#elif/#else/#endif lines before tree-sitter parsing |
| 2b | Tree-sitter validation (SARD) | Confirm function_definition node exists at root level |
| 2c | Function extraction (non-SARD) | extract_functions() splits full C files into individual functions |
| 3 | Comment removal | Strip // line comments and /* */ block comments |
| 4 | Blank line normalization | Collapse 3+ consecutive newlines to 2 |
| 5 | Line filter | Reject if < 5 or > 500 lines |
| 6 | Token filter | Reject if < 10 or > 4096 whitespace-delimited tokens |

⛔ CRITICAL SARD samples (source='sard') already have a single extracted function in the code field — process_sard.py did this in Phase 2. Stage 1 must NOT re-run extract_functions() on them. Branch on source == 'sard' before any extraction logic.

⚠ WARNING Juliet #ifdef stripping is MANDATORY before tree-sitter parsing. Juliet wraps functions in #ifndef OMITBAD / #ifndef OMITGOOD guards. Without stripping, Joern in Stage 4 produces incomplete CPGs. Expect ~15–20% rejection rate on short good() functions that fall below 5-line minimum after stripping.

## 2.2 Source-Specific Branching

| Source | Stage 1 Action |
| --- | --- |
| sard | Skip extract_functions(). Strip #ifdef guards. Validate has function_definition. Normalize. |
| exploitdb | Run extract_functions() on full file. May yield multiple functions per exploit. |
| cve / cve_cfa | Run extract_functions() on before/after code. Code field is already function-level diff. |
| github_advisory | Run extract_functions(). May contain full file — extract relevant functions. |
| osv | Same as github_advisory. |
| repo / repo_cfa | Run extract_functions() on before/after commit diff. |

## 2.3 Claude Code Prompt

▶ CLAUDE CODE PROMPT

Read docs/PREPROCESSING.md §Stage 1 completely. Read training/scripts/collection/schema.py to understand VALID_SOURCES. Read training/scripts/collection/base_collector.py for existing patterns. Build training/scripts/preprocessing/stage1_clean.py with the following structure: == IMPORTS AND CONSTANTS == from tree_sitter import Language, Parser import tree_sitter_c as tsc C_LANGUAGE = Language(tsc.language()) parser = Parser(C_LANGUAGE) MIN_LINES = 5; MAX_LINES = 500; MIN_TOKENS = 10; MAX_TOKENS = 4096 SARD_SOURCES = {"sard", "sard_cfa"} == FUNCTION: strip_preprocessor_guards(code: str) -> str == Remove lines matching: #\s*(ifdef¦ifndef¦elif¦else¦endif)[^\n]*\n Must be called BEFORE comment removal for SARD samples. == FUNCTION: extract_functions(source: str, filepath: str = "") -> list[dict] == Use tree-sitter C parser. Walk root_node.children. Only collect nodes where node.type == "function_definition". Return list of {code, name, start_line, end_line, filepath}. This function is used ONLY for non-SARD sources. == FUNCTION: normalize(code: str, source: str = "") -> str ¦ None == Steps in order: 1. If source in SARD_SOURCES: call strip_preprocessor_guards(code) first 2. Remove // comments: re.sub(r'//[^\n]*', '', code) 3. Remove /* */ comments: re.sub(r'/\*.*?\*/', '', code, flags=re.DOTALL) 4. Normalize blank lines: re.sub(r'\n{3,}', '\n\n', code).strip() 5. Line filter: lines = code.splitlines(); if not (MIN_LINES <= len(lines) <= MAX_LINES): return None 6. Token filter: tokens = code.split(); if not (MIN_TOKENS <= len(tokens) <= MAX_TOKENS): return None 7. Return normalized code == FUNCTION: process_sample(sample: dict) -> list[dict] ¦ None == Handle encoding (chardet if bytes). Branch on source: If source in SARD_SOURCES: Validate tree-sitter sees function_definition at root level. Call normalize(code, source). Return [updated_sample] or None. Else: Call extract_functions(code). For each extracted fn: call normalize(fn.code). Return list of updated samples (one per extracted function), or None if all fail. For multi-function files: each child sample inherits parent label, cwe, pair_id, and gets function_name/start_line/end_line added to metadata. == FUNCTION: run_stage1(input_paths: list[str], output_path: str, dry_run: bool, max_samples: int) == Read all *.jsonl files from input_paths. For each sample: call process_sample(). Write results to output_path. Track: processed, skipped, total_in, total_out. Print summary at end. Use atomic write: write to output_path + '.tmp', then os.replace(). == CLI FLAGS == --input: one or more directories/files containing .jsonl files --output: default training/data/processed/cleaned/samples.jsonl --dry-run: process but don't write output --max-samples N: stop after N successfully processed samples --source-filter: only process samples from specific source (e.g., sard) == TESTS: tests/test_story_p3s1.py — 12 tests == 1. strip_preprocessor_guards removes #ifdef/#ifndef/#endif lines 2. strip_preprocessor_guards preserves code between guards 3. normalize removes // comments 4. normalize removes /* */ block comments 5. normalize rejects code under 5 lines 6. normalize rejects code over 500 lines 7. normalize rejects code under 10 tokens 8. SARD path: code with #ifdef → stripped before comment removal 9. SARD path: no function_definition → returns None 10. non-SARD path: full file → multiple functions extracted 11. Dry run: no output file written 12. max-samples: stops at limit

## 2.4 Checkpoint Verification

✓ CHECKPOINT # Dry run with 20 SARD samples python training/scripts/preprocessing/stage1_clean.py \ --input training/scripts/collection/data/raw/sard/ \ --output training/data/processed/cleaned/samples.jsonl \ --dry-run --max-samples 20 # Full run on all sources python training/scripts/preprocessing/stage1_clean.py \ --input data/raw/merged/ \ --output training/data/processed/cleaned/samples.jsonl # Verify output python -c " import json samples = [json.loads(l) for l in open('training/data/processed/cleaned/samples.jsonl')] print('Total:', len(samples)) # Check no #ifdef remains ifdef_count = sum(1 for s in samples if '#ifdef' in s['code'] or '#ifndef' in s['code']) print('Samples with #ifdef remaining:', ifdef_count) assert ifdef_count == 0, 'SARD #ifdef stripping failed!' print('CHECKPOINT PASS')" # Expected: 44,000–48,000 samples from SARD (after ~15-20% rejection from short functions)

## 2.5 Production Issues for Stage 1

| Issue | Impact | Fix |
| --- | --- | --- |
| tree-sitter API changed in 0.22+ | Language.build_library() no longer exists — crash on import | Use Language(tsc.language()) — NOT Language.build_library(). Pin tree-sitter>=0.22. |
| SARD multi-function files | Some Juliet .c files have both bad() and good() in same file — process_sard.py already extracted individual functions, but some other SARD variants may not | Check source field: if 'sard' skip extraction. Log any SARD file where multiple function_definitions found. |
| chardet slow on large files | chardet on 400-line C files: ~20ms each × 40K samples = 13 minutes added overhead | Only call chardet if the fast UTF-8 decode raises UnicodeDecodeError. Most files are UTF-8. |
| Non-function C code snippets | Some CVE/ExploitDB entries contain struct definitions or includes, not function bodies. tree-sitter finds 0 functions. | Log these to stage1_no_functions.jsonl. Do NOT error — silently skip with counter. |
| Long functions after comment removal | A function with 600 lines of comments + 100 lines code passes 500-line filter BEFORE stripping comments but should be caught after. Run length check AFTER comment removal. | Always run line/token filter AFTER comment removal. Never pre-filter on raw code. |

# 3. Story P3-S2 — Stage 2: Deduplicate

| Item | Detail |
| --- | --- |
| File to build | training/scripts/preprocessing/stage2_dedup.py |
| Test file | tests/test_story_p3s2.py |
| Input | training/data/processed/cleaned/samples.jsonl |
| Output | training/data/processed/deduped/samples.jsonl |
| Duration | 1–2 hours for 40K samples |
| Depends on | Stage 1 complete |

## 3.1 Four Deduplication Levels

Stage 2 runs four levels of deduplication in sequence. Each level catches what the previous missed. ALL levels must run — skipping any level leaves duplicates that inflate apparent dataset size and can cause test/train leakage.

| Level | Method | What It Catches | Time |
| --- | --- | --- | --- |
| L1: Exact | MD5 hash of whitespace-normalized code | Exact copies, copy-paste from same CVE in multiple sources | ~1 min |
| L2: CVE-ID | Group by (cve_id, file_path) | Same CVE fix collected from NVD + GitHub Advisory + OSV simultaneously | ~1 min |
| L3: Commit SHA | Group by (commit_sha, file_path) | Same GitHub commit fetched by CVE collector and Repo Miner | ~1 min |
| L4: MinHash LSH | Jaccard similarity >= 0.85, 128 permutations, 4-gram shingles | Juliet goodG2B1/goodG2B2 variants, near-identical patches | 30–60 min |

⛔ CRITICAL After MinHash dedup, RE-CHECK pair integrity. L4 MinHash may remove one side of a CFA pair (if it matches another safe function at 85%+ Jaccard). If pair_id has only one side remaining: set pair_id='' on the survivor. Never leave a half-pair in the dataset.

## 3.2 Claude Code Prompt

▶ CLAUDE CODE PROMPT

Read docs/PREPROCESSING.md §Stage 2 completely. Build training/scripts/preprocessing/stage2_dedup.py == FUNCTION: md5_normalize(code: str) -> str == hashlib.md5(" ".join(code.split()).encode()).hexdigest() == FUNCTION: level1_exact(samples: list) -> list == seen = {} For each sample: compute h = md5_normalize(sample["code"]) If h not in seen: seen[h] = sample Return list(seen.values()) Report: N removed == FUNCTION: level2_cve_id(samples: list) -> list == seen = set(); result = [] For each sample: cve = sample.get("cve_id") key = (cve, sample.get("file_path", "")) if cve else None If not key OR key not in seen: result.append(sample) If key: seen.add(key) Report: N removed == FUNCTION: level3_commit_sha(samples: list) -> list == seen = {}; result = [] For each sample: sha = sample.get("commit_sha") key = (sha, sample.get("file_path", "")) if sha else None If not key OR key not in seen: result.append(sample) If key: seen[key] = True Report: N removed == FUNCTION: level4_minhash_lsh(samples: list, threshold: float = 0.85) -> list == from datasketch import MinHash, MinHashLSH lsh = MinHashLSH(threshold=threshold, num_perm=128) result = [] For each sample i: m = MinHash(num_perm=128) code = " ".join(sample["code"].split()) For j in range(len(code) - 3): m.update(code[j:j+4].encode()) If lsh.query(m) is empty: lsh.insert(str(i), m); result.append(sample) Return result Report: N removed IMPORTANT: For large datasets (>40K) use num_perm=64 instead of 128 for 2x speed. Add: num_perm = 64 if len(samples) > 40_000 else 128 == FUNCTION: repair_broken_pairs(samples: list) -> list == CRITICAL — run this AFTER level4_minhash_lsh. pairs = {} For each sample with pair_id: pairs.setdefault(pair_id, []).append(sample["label"]) For each sample: if pair_id and pairs[pair_id] doesn't have both 0 and 1: sample = {**sample, "pair_id": ""} # clear orphaned pair_id Return updated list. Report: N pairs repaired (orphaned) == FUNCTION: run_stage2(input_path: str, output_path: str, dry_run: bool) == samples = load all from input_path print("Input:", len(samples)) s = level1_exact(samples); print("After L1:", len(s)) s = level2_cve_id(s); print("After L2:", len(s)) s = level3_commit_sha(s); print("After L3:", len(s)) s = level4_minhash_lsh(s); print("After L4:", len(s)) s = repair_broken_pairs(s); print("After pair repair:", len(s)) Write to output_path atomically. == CLI FLAGS == --input, --output, --dry-run, --threshold (default 0.85) == TESTS: tests/test_story_p3s2.py — 10 tests == 1. L1 removes exact whitespace-normalized duplicate 2. L1 keeps samples with different code 3. L2 removes same (cve_id, file_path) pair 4. L2 keeps samples with different cve_id 5. L3 removes same (commit_sha, file_path) pair 6. L4 removes near-duplicate (>85% Jaccard) 7. L4 keeps sufficiently different samples 8. repair_broken_pairs clears pair_id on orphaned sample 9. repair_broken_pairs leaves valid pairs intact 10. Full pipeline: 10 samples with 3 dups → correct final count

## 3.3 Checkpoint Verification

✓ CHECKPOINT python training/scripts/preprocessing/stage2_dedup.py \ --input training/data/processed/cleaned/samples.jsonl \ --output training/data/processed/deduped/samples.jsonl # Expected output: # After L1 exact: ~44000 (minimal reduction) # After L2 CVE-ID: ~43500 (small reduction) # After L3 SHA: ~42000 (moderate from cross-source) # After L4 LSH: ~32000–38000 (Juliet near-dups removed) # After pair repair: ~32000–38000 (broken pairs cleared) # Verify pair integrity python -c " import json s = [json.loads(l) for l in open('training/data/processed/deduped/samples.jsonl')] pairs = {} for x in s: if x.get('pair_id'): pairs.setdefault(x['pair_id'], set()).add(x['label']) broken = {k:v for k,v in pairs.items() if len(v) < 2} print('Total:', len(s)) print('Valid pairs:', sum(1 for v in pairs.values() if len(v)==2)) print('Broken pairs:', len(broken)) assert len(broken) == 0, 'BROKEN PAIRS AFTER DEDUP!' print('CHECKPOINT PASS')"

## 3.4 Production Issues for Stage 2

| Issue | Impact | Fix |
| --- | --- | --- |
| datasketch memory for large datasets | MinHashLSH with 40K+ samples and num_perm=128 uses ~2–3 GB RAM | Use num_perm=64 if len > 40K. Process in batches of 10K if OOM. |
| L4 removes one side of SARD native CFA pair | safe goodG2B1 removed as near-dup of goodG2B2 — leaves vulnerable bad() orphaned | repair_broken_pairs() is MANDATORY after L4. This is a known SARD issue. |
| 4-gram shingles on very short code | Functions with < 4 chars don't produce shingles — MinHash always matches empty shingle set | Pre-filter: skip MinHash for samples with < 50 chars. They'll be caught by L1 exact instead. |
| Cross-source SHA format differences | Short SHA from NVD (7 chars) vs full SHA from OSV (40 chars) — L3 misses them as 'different' | SHA normalization should have been done in Phase 2 collectors. If not: normalize all SHAs to 40 chars before L3. Use GitHub API to expand short SHAs. |

# 4. Story P3-S3 — Stage 3: CFA Generation

| Item | Detail |
| --- | --- |
| File to build | training/scripts/preprocessing/stage3_cfa.py |
| Test file | tests/test_story_p3s3.py |
| Input | training/data/processed/deduped/samples.jsonl (label=1 samples only) |
| Output | training/data/processed/with_cfa/samples.jsonl (originals + CFA pairs) |
| Duration | 22+ hours (API rate limited: ~3 CFA per vulnerable sample × 30K+ vuln samples) |
| Depends on | Stage 2 complete, ANTHROPIC_API_KEY set, gcc available |
| API cost | ~$0.25 per 1000 CFA generations (Claude Haiku 4.5) |

⛔ CRITICAL CFA pairs (vulnerable + counterfactual) are the PRIMARY research novelty of StreamGuard. The contrastive loss L_CFA is meaningless without them. If Stage 3 produces broken or low-quality pairs, the paper's core claim (CFA improves F1) will not hold. Quality > quantity: 2 validated CFAs per sample beats 10 unvalidated ones.

## 4.1 Per-CWE Prompt Templates

Generic prompts fail. 'Fix the vulnerability' produces bad CFAs for UAF (model pads with malloc checks) and SQL injection (model just escapes quotes). Each CWE needs the exact correct fix strategy.

| CWE | Vulnerability Pattern | CFA Fix Instruction | Expected Changed Lines |
| --- | --- | --- | --- |
| CWE-120 | strcpy/gets/strcat/sprintf with no bounds | Replace with strncpy/fgets/strncat/snprintf + explicit size | 1–3 lines |
| CWE-89 | sprintf+query string concat into SQL | Replace with parameterized statement (sqlite3_prepare_v2, mysql_stmt) | 3–8 lines |
| CWE-78 | system(user_str) or popen(user_str) | Replace with execve() with fixed argv[] or whitelist validation | 3–6 lines |
| CWE-416 | free(ptr) then use ptr | Add ptr=NULL after free(); add NULL check before use | 2–4 lines |
| CWE-476 | deref without NULL check | Add if(ptr==NULL) return ERROR before deref | 1–2 lines |
| CWE-134 | printf(user_str) format string | Replace with printf("%s", user_str) | 1 line |
| CWE-190 | a+b with no overflow check | Add if(a > INT_MAX-b) return ERROR before operation | 2–3 lines |
| CWE-121/122 | array write without bounds check | Add index < array_size check before write | 1–3 lines |
| CWE-125 | array read without bounds | Add bounds check before read | 1–2 lines |
| CWE-79 | C web output injection | Escape output using HTML entity encoding | 2–4 lines |
| CWE-119 | general buffer operation | Add explicit size limits and bounds validation | 2–4 lines |

## 4.2 CFA Validation Gates

Every LLM-generated CFA must pass ALL four gates before being saved:

| Gate | Method | Pass Condition | Fail Action |
| --- | --- | --- | --- |
| Gate 1: Differs from original | String comparison | cfa_code.strip() != original.strip() | Reject — LLM returned unchanged code |
| Gate 2: Similarity bounds | SequenceMatcher ratio on split tokens | 0.60 <= sim <= 0.99 | Reject — too similar (no fix) or too different (hallucination) |
| Gate 3: Compilation check | gcc -fsyntax-only -w on temp .c file | Return code == 0 | Reject — invalid C syntax |
| Gate 4: Vulnerability pattern removed | CWE-specific regex on cfa_code | No match — pattern is gone | Reject — fix didn't address the vulnerability |

## 4.3 Claude Code Prompt

▶ CLAUDE CODE PROMPT

Read docs/PREPROCESSING.md §Stage 3 completely. Read docs/PREPROCESSING.md §CFA_PROMPTS dict — use these EXACTLY. Read training/scripts/collection/schema.py for VALID_CWE and VALID_SOURCES. Build training/scripts/preprocessing/stage3_cfa.py == CFA_PROMPTS dict (implement all 12 CWEs) == Use the exact prompts from PREPROCESSING.md §Stage 3 §Per-CWE Prompt Templates. Key points: - Each prompt ends with: "Output ONLY the corrected C function. No explanation." - CWE-79 uses same pattern as CWE-89 (similar sanitization) - CWE-119 uses same pattern as CWE-120 (general buffer overflow) == VULN_PATTERNS dict (CWE-specific regex for Gate 4) == VULN_PATTERNS = { "CWE-120": [r'\bstrcpy\s*\(', r'\bgets\s*\(', r'\bstrcat\s*\('], "CWE-89": [r'sprintf\s*\([^,]+,\s*[^"]*%s', r'mysql_query\s*\(.*\+'], "CWE-78": [r'system\s*\(.*argv', r'popen\s*\(.*user'], "CWE-134": [r'printf\s*\(\s*\w+\s*\)', r'fprintf\s*\([^,]+,\s*\w+\s*\)'], "CWE-416": [r'free\s*\(\w+\)(?!\s*;\s*\w+\s*=\s*NULL)'], "CWE-190": [r'\+\s*\w+\s*(?!.*INT_MAX)', r'\*\s*\w+\s*(?!.*overflow)'], "CWE-476": [r'\*\w+\s*(?!.*!=\s*NULL)(?!.*==\s*NULL)'], "CWE-121": [r'\bstrcpy\s*\(', r'\bwcscpy\s*\('], "CWE-122": [r'\bmemcpy\s*\(.*\+', r'heap.*overflow'], "CWE-125": [r'\w+\[\w+\](?!.*<.*len)', r'\w+\[\w+\](?!.*size)'], } == FUNCTION: generate_cfa(code: str, cwe: str) -> str ¦ None == from anthropic import Anthropic client = Anthropic() prompt = CFA_PROMPTS.get(cwe, CFA_PROMPTS["CWE-120"]) Call client.messages.create( model="claude-haiku-4-5", max_tokens=1024, messages=[{"role": "user", "content": "VULNERABLE C FUNCTION:\n```c\n{code}\n```\n\nTASK:\n{prompt}"}] ) Return msg.content[0].text Wrap in try/except — return None on any API error Add tenacity retry: 3 attempts, wait_exponential(min=5, max=60) on anthropic.APIError == FUNCTION: extract_c_code(llm_response: str) -> str == Try regex: re.search(r'```(?:c)?\n(.*?)[BACKTICK3]', response, re.DOTALL) If match: return match.group(1).strip() Else: return response.strip() == FUNCTION: validate_cfa(original: str, cfa_raw: str, cwe: str) -> tuple[bool, str, str] == Returns (is_valid, rejection_reason, cleaned_cfa_code) cfa_code = extract_c_code(cfa_raw) Gate 1: if cfa_code.strip() == original.strip(): return False, "identical_to_original", "" Gate 2: sim = SequenceMatcher(None, original.split(), cfa_code.split()).ratio() if sim > 0.99: return False, "too_similar", "" if sim < 0.60: return False, "too_different", "" Gate 3: Write wrapper = "#include <stdio.h>\n#include <string.h>\n#include <stdlib.h>\n" + cfa_code to temp file. Run: subprocess.run(["gcc", "-fsyntax-only", "-w", fname], timeout=15) if returncode != 0: return False, "compile_fail", "" Gate 4: for pat in VULN_PATTERNS.get(cwe, []): if re.search(pat, cfa_code, re.IGNORECASE): return False, "vuln_pattern_remains", "" return True, "", cfa_code == FUNCTION: run_stage3(input_path: str, output_path: str, target_ratio: float = 2.0, dry_run: bool, max_samples: int) == Load samples from input_path. Track: total_vuln, total_cfa_generated, total_cfa_accepted, compile_rate, pattern_removal_rate. For each sample: Write original sample to output (all samples — not just vulnerable). If sample["label"] != 1: continue If not sample.get("cwe"): continue cwe = sample["cwe"] pair_id = sample.get("pair_id") or str(uuid.uuid4()) Update original sample's pair_id to this value. attempts = 0; cfa_count = 0 While cfa_count < target_ratio and attempts < 6: attempts += 1 raw = generate_cfa(sample["code"], cwe) if not raw: continue valid, reason, cfa_code = validate_cfa(sample["code"], raw, cwe) if not valid: log to cfa_failures dict: {reason: count} continue cfa_sample = { **sample, "id": str(uuid.uuid4()), "code": cfa_code, "label": 0, "pair_id": pair_id, "cfa_type": "llm_generated", "source": sample["source"] + "_cfa", } Write cfa_sample to output. cfa_count += 1 Checkpoint: every 200 samples, save {last_processed_id, samples_done, cfa_count, compile_rate}. On resume: skip already-processed sample IDs. Print final stats: compile_rate = accepted / (generated) * 100 pattern_removal_rate = (accepted) / (not_identical_not_too_diff) * 100 avg_cfa_per_vuln_sample == CLI FLAGS == --input, --output, --dry-run, --max-samples N --target-ratio (default 2.0: aim for 2 CFAs per vulnerable sample) --cwe-filter (only generate CFA for specific CWE, for testing) --checkpoint-dir == TESTS: tests/test_story_p3s3.py — 12 tests == 1. extract_c_code: extracts from ```c...[BACKTICK3] markdown fence 2. extract_c_code: returns raw text when no fence found 3. validate_cfa Gate 1: identical code rejected 4. validate_cfa Gate 2a: >0.99 similarity rejected 5. validate_cfa Gate 2b: <0.60 similarity rejected 6. validate_cfa Gate 3: invalid C syntax rejected (mock gcc returning 1) 7. validate_cfa Gate 4: vulnerability pattern still present → rejected 8. validate_cfa: all gates pass → (True, "", code) returned 9. run_stage3 dry-run: no output written 10. Checkpoint: processed IDs skipped on resume 11. CFA sample has label=0, pair_id matches original 12. source tag: original "sard" → CFA "sard_cfa"

## 4.4 Checkpoint Verification

✓ CHECKPOINT # ALWAYS test on 5 samples first (CFA generation costs API credits) python training/scripts/preprocessing/stage3_cfa.py \ --input training/data/processed/deduped/samples.jsonl \ --output training/data/processed/with_cfa/samples.jsonl \ --dry-run --max-samples 5 --cwe-filter CWE-120 # Expected output for dry run: # CWE-120 ¦ Original: void CWE120_bad() {... ¦ CFA generated: void CWE120_bad() {... (strncpy version) # Gate results: [compile: PASS] [pattern: PASS] [similarity: 0.82] # Full run (background process — takes 22+ hours) nohup python training/scripts/preprocessing/stage3_cfa.py \ --input training/data/processed/deduped/samples.jsonl \ --output training/data/processed/with_cfa/samples.jsonl \ --target-ratio 2.0 > logs/stage3_cfa.log 2>&1 & # Monitor progress tail -f logs/stage3_cfa.log ¦ grep -E "compile_rate¦pattern_removal¦ETA" # Final verification python -c " import json from collections import Counter s = [json.loads(l) for l in open('training/data/processed/with_cfa/samples.jsonl')] cfa = [x for x in s if x.get('cfa_type') == 'llm_generated'] print('Total samples:', len(s)) print('CFA generated:', len(cfa)) print('CFA per CWE:', Counter(x['cwe'] for x in cfa).most_common()) pairs = {} for x in s: if x.get('pair_id'): pairs.setdefault(x['pair_id'], set()).add(x['label']) broken = {k:v for k,v in pairs.items() if len(v)<2} print('Valid CFA pairs:', sum(1 for v in pairs.values() if len(v)==2)) print('Broken pairs:', len(broken)) assert len(broken) == 0 print('CHECKPOINT PASS')" # Target metrics: # compile_rate >= 80% # pattern_removal_rate >= 60% # avg_cfa_per_vuln_sample >= 1.5

## 4.5 Production Issues for Stage 3

| Issue | Impact | Fix |
| --- | --- | --- |
| API rate limit (Claude Haiku) | Anthropic API has request/minute limits — 22+ hours of generation will hit them | Wrap in tenacity with exponential backoff. Check for anthropic.RateLimitError specifically. Sleep 60s on rate limit. |
| LLM returns explanation instead of code | Many responses start with 'Here is the fixed...' before the code. extract_c_code() must handle this. | Always try markdown fence extraction first. Fall back to extracting first code-like block starting with 'void' or return type. |
| gcc not in PATH on Windows | subprocess.run(['gcc',...]) raises FileNotFoundError — crashes for every CFA | Check shutil.which('gcc') on startup. If None: print error with MinGW install instructions. Still run Gates 1/2/4 — skip Gate 3 with warning. |
| pair_id collision — SARD samples already have pair_id | SARD native pairs have pair_id from Phase 2. Generating LLM CFA for SARD would overwrite with new pair_id. | Check: if sample['cfa_type'] == 'native' or source == 'sard': skip CFA generation. SARD already has native pairs. |
| Stage 3 output file grows to multi-GB | with_cfa/samples.jsonl with 3× augmentation = 90K–120K lines. Reading all into memory for resume check is slow. | Checkpoint tracks processed sample IDs (not re-reading output JSONL). Use set of IDs for O(1) skip check. |
| API cost overrun | Generating 3 CFAs per 20K vulnerable samples × 6 attempts = 360K API calls. At $0.25/1K = $90 total. | Use target_ratio=2.0 (not 3.0) for Phase 1. Increase to 3.0 only for underrepresented CWEs. Monitor spend daily. |

# 5. Story P3-S4 — Stage 4: CPG Construction

| Item | Detail |
| --- | --- |
| File to build | training/scripts/preprocessing/stage4_cpg.py + joern_scripts/generate_cpg.sc |
| Test file | tests/test_story_p3s4.py (extend test_story5.py from Phase 1) |
| Input | training/data/processed/with_cfa/samples.jsonl |
| Output | training/data/processed/cpg/{shard}/{sample_id}.json |
| Duration | 3–4 days at 2 workers (Joern: ~12s/sample cold start) |
| Depends on | Stage 3 complete, JOERN_BIN env set, Joern 4.x installed (JVM 17+) |

⛔ CRITICAL run.ossdataflow is the #1 critical path in the entire system. In Joern 4.x CLI pipeline (joern-parse), data flow is included by default. In Joern REPL mode you must call run.ossdataflow explicitly. Verify DFG edges exist in the first 5 CPG outputs — if dfg_edge_total == 0 on all of them, STOP and fix before running on all 40K samples.

## 5.1 Pipeline per Sample (10 Steps)

| Step | Operation | Details |
| --- | --- | --- |
| 1 | Write to temp .c file | Prepend JULIET_STUB for SARD samples. Strip SARD-specific #include statements. |
| 2 | joern-parse sample.c -o cpg.bin | Generates CPG binary with default overlays (includes DFG in Joern 4.x) |
| 3 | joern-export cpg.bin -o export/ --repr cpg --format graphson | Exports TinkerGraph JSON format |
| 4 | Parse GraphSON TinkerGraph | Per-method subdirs each with export.json. Merge all methods. |
| 5 | Filter edges | Keep AST(0), CFG(1), DFG(2) only. DROP CDG, DOMINATE, CONTAINS, ARGUMENT, REF. |
| 6 | Label taint roles on nodes | SOURCE/SINK/SANITIZER/PROPAGATION/NONE on CALL nodes only |
| 7 | Build TPG edges (Novel N3) | BFS from SOURCE nodes to SINK nodes along DFG. Add TAINT edge type (3). |
| 8 | Context slice | 2-hop BFS from taint seed nodes, max 200 nodes |
| 9 | Validate | nodes >= 3, DFG edges > 0, no NaN, edge_index.max() < num_nodes |
| 10 | Save CPG JSON | Sharded output: cpg/{first_2_chars_of_id}/{sample_id}.json |

⚠ WARNING CDG edges MUST be dropped before saving. Storing CDG as edge_type >= 4 causes CUDA index-out-of-bounds crash during GGNN training. The model expects exactly 4 edge types: AST=0, CFG=1, DFG=2, TPG=3. Any edge with type >= 4 silently corrupts training.

## 5.2 Taint Analysis Configuration

The taint analysis labels nodes with roles and builds the TPG — the novel 4th CPG component. Restrict to CALL nodes only to prevent BLOCK/METHOD nodes from false-tagging.

| Role | Function Names |
| --- | --- |
| SOURCES | scanf, gets, fgets, getenv, recv, read, fread, getchar, fscanf, sscanf, getc, fgetc, fgetws, wscanf, fwscanf, connect, accept, listen, atoi, strtol, strtoul |
| SINKS | strcpy, strcat, system, popen, mysql_query, sprintf, printf, fprintf, execve, execl, execvp, printLine, printIntLine, printHexCharLine, free, realloc, wcscpy, wcscat, wmemcpy, malloc (when size is taint-controlled) |
| SANITIZERS | strncpy, strncat, snprintf, validate, sanitize, escape, filter, check, whitelist |
| OPERATOR SINKS | <operator>.indirectIndexAccess, <operator>.indexAccess (catches buffer[index] patterns) |

## 5.3 JULIET_STUB Header

Prepend to ALL SARD samples before Joern processing. Without these stubs, Joern produces incomplete CPGs for printLine/printIntLine calls.

#include <stdio.h>

#include <stdlib.h>

#include <string.h>

void printLine(const char* msg) {}

void printIntLine(int i) {}

void printDoubleLine(double d) {}

void printHexCharLine(char c) {}

void printLongLine(long l) {}

void printLongLongLine(long long ll) {}

void printUnsignedLine(unsigned u) {}

void printSizeTLine(size_t s) {}

## 5.4 Claude Code Prompt

▶ CLAUDE CODE PROMPT

Read docs/PREPROCESSING.md §Stage 4 completely. Read docs/ARCHITECTURE.md §CPG Construction completely. Read docs/NOVELTY.md §N3 (TPG as 4th CPG component). Read training/scripts/preprocessing/stage4_cpg.py from Phase 1 (Story 5) as the base. This story extends the Phase 1 Stage 4 implementation to handle the FULL dataset (not just SARD). Key changes from Phase 1: 1. Add non-SARD source handling (no JULIET_STUB for CVE/repo samples) 2. Extend taint SOURCE/SINK sets to cover all 12 CWEs 3. Add output_param_functions for recv/fscanf BFS seed injection 4. Full checkpoint/resume for 40K samples == JULIET_STUB constant == JULIET_STUB = """ #include <stdio.h> #include <stdlib.h> #include <string.h> void printLine(const char* msg) {} void printIntLine(int i) {} void printDoubleLine(double d) {} void printHexCharLine(char c) {} void printLongLine(long l) {} void printLongLongLine(long long ll) {} void printUnsignedLine(unsigned u) {} void printSizeTLine(size_t s) {} """ SARD_STRIP_INCLUDES = {"std_testcase.h", "std_testcase_io.h", "std_thread.h"} == FUNCTION: write_temp_c(sample: dict, tmpdir: Path) -> Path == path = tmpdir / f"{sample['id']}.c" content = sample['code'] # For SARD: prepend JULIET_STUB and strip custom #include lines if sample.get('source', '').startswith('sard'): lines = content.splitlines() filtered = [l for l in lines if not any(inc in l for inc in SARD_STRIP_INCLUDES)] content = JULIET_STUB + "\n" + "\n".join(filtered) else: content = "#include <stdio.h>\n#include <string.h>\n#include <stdlib.h>\n" + content path.write_text(content, encoding='utf-8') return path == EDGE TYPE MAP (4 types ONLY — no CDG) == EDGE_TYPE_MAP = { "AST": 0, "CFG": 1, "REACHING_DEF": 2, "REACHES": 2, # DFG (Joern uses REACHING_DEF in 4.x) "TPG": 3 # Added by Python post-processor } # IMPORTANT: Any edge label NOT in this map is DROPPED silently. # CDG, DOMINATE, POST_DOMINATE, CONTAINS, ARGUMENT, REF → all dropped. == TAINT LABELING (CALL nodes only) == def _get_taint_role(node) -> str: if node.get('_label') != 'CALL': return 'NONE' name = node.get('name', '').lower() if any(s in name for s in SOURCES): return 'SOURCE' if any(s in name for s in SANITIZERS): return 'SANITIZER' if any(s in name for s in SINKS): return 'SINK' if node.get('code','').find('<operator>.indirectIndexAccess') >= 0: return 'SINK' return 'NONE' == BFS TPG CONSTRUCTION == def build_tpg_edges(nodes, dfg_edges): source_ids = [n['id'] for n in nodes if n.get('taint_role') == 'SOURCE'] sink_ids = set(n['id'] for n in nodes if n.get('taint_role') == 'SINK') sanitizer_ids = set(n['id'] for n in nodes if n.get('taint_role') == 'SANITIZER') tpg_edges = [] for src_id in source_ids: # BFS along DFG edges from src_id to any sink visited = {src_id} queue = [(src_id, [src_id])] while queue: curr, path = queue.pop(0) if curr in sink_ids and len(path) > 1: # Found taint path — add TPG edges along path for i in range(len(path)-1): tpg_edges.append({"src": path[i], "dst": path[i+1], "type": 3, "label": "TPG"}) # Label intermediate nodes as PROPAGATION if path[i] not in source_ids and path[i] not in sink_ids: [n for n in nodes if n['id'] == path[i]][0]['taint_role'] = 'PROPAGATION' break if curr in sanitizer_ids: continue # Stop at sanitizer for edge in dfg_edges: if edge['src'] == curr and edge['dst'] not in visited: visited.add(edge['dst']); queue.append((edge['dst'], path + [edge['dst']])) return tpg_edges == CONTEXT SLICING (max 200 nodes) == def context_slice(nodes, edges, max_nodes=200): if len(nodes) <= max_nodes: return nodes, edges taint_ids = set(n['id'] for n in nodes if n.get('taint_role') != 'NONE') if not taint_ids: # No taint: keep first max_nodes by connectivity return nodes[:max_nodes], [e for e in edges if e['src'] in {n['id'] for n in nodes[:max_nodes]} and e['dst'] in {n['id'] for n in nodes[:max_nodes]}] # 2-hop BFS from taint seeds adj = {} for e in edges: adj.setdefault(e['src'], set()).add(e['dst']); adj.setdefault(e['dst'], set()).add(e['src']) included = set(taint_ids) frontier = set(taint_ids) for _ in range(2): new_frontier = set() for nid in frontier: for neighbor in adj.get(nid, set()): if neighbor not in included: new_frontier.add(neighbor); included.add(neighbor) frontier = new_frontier if len(included) >= max_nodes: break included = set(list(included)[:max_nodes]) sliced_nodes = [n for n in nodes if n['id'] in included] sliced_edges = [e for e in edges if e['src'] in included and e['dst'] in included] return sliced_nodes, sliced_edges == MAIN PROCESSING FUNCTION: process_one_sample(sample, joern_dir, output_dir) == 1. Create tempdir 2. Write temp .c file (with JULIET_STUB for SARD) 3. Run: joern-parse {tmpfile} -o {tmpdir}/cpg.bin (timeout=60s) 4. Run: joern-export {tmpdir}/cpg.bin -o {tmpdir}/export --repr cpg --format graphson (timeout=60s) 5. Parse GraphSON: find all export.json in subdirs, merge nodes+edges 6. Filter edges: only keep types in EDGE_TYPE_MAP 7. Label taint roles on nodes 8. Build TPG edges via BFS 9. Context slice to max 200 nodes 10. Validate: len(nodes) >= 3, dfg_count > 0, no NaN 11. Save to output_dir/{id[:2]}/{id}.json 12. Return stats dict {dfg_edges, tpg_edges, taint_nodes, success: True/False} == CHECKPOINT / RESUME == Save checkpoint every 500 samples: {processed_ids: [...], stats: {...}} On startup: load checkpoint, build set of already-processed IDs Skip samples whose ID is in already-processed set == PAIR-AWARE DISCARD == After ALL samples processed: Scan for pair_id groups where any member FAILED cpg construction. Remove cpg JSON files for the surviving partner too. Report: N broken pairs removed. == CLI FLAGS == --input, --output, --workers (default 2), --dry-run, --max-samples N --joern-dir (default: JOERN_BIN env parent), --checkpoint-dir == TESTS: tests/test_story_p3s4.py — 15 tests == Extend test_story5.py from Phase 1 with 5 additional tests: 1. SARD source: JULIET_STUB prepended to temp file 2. non-SARD source: no JULIET_STUB, only standard includes 3. CDG edge dropped from EDGE_TYPE_MAP 4. REACHING_DEF mapped to type 2 (DFG) — Joern 4.x specific 5. Pair-aware discard: if partner fails, survivor's CPG is removed

## 5.5 Checkpoint Verification

✓ CHECKPOINT # Dry run on 5 samples python training/scripts/preprocessing/stage4_cpg.py \ --input training/data/processed/with_cfa/samples.jsonl \ --output training/data/processed/cpg/ \ --dry-run --max-samples 5 # CRITICAL: verify DFG edges exist in first 5 CPGs python -c " import json, glob cpgs = list(glob.glob('training/data/processed/cpg/**/*.json', recursive=True))[:5] for f in cpgs: d = json.load(open(f)) dfg = [e for e in d['edges'] if e['type'] == 2] tpg = [e for e in d['edges'] if e['type'] == 3] print(f'{f}: DFG={len(dfg)} TPG={len(tpg)} taint_nodes={sum(1 for n in d["nodes"] if n.get("taint_role") != "NONE")}')" # IF DFG COUNT IS 0 ON ALL FILES: STOP. Fix Joern setup before continuing. # Full run (background, 2 workers) nohup python training/scripts/preprocessing/stage4_cpg.py \ --input training/data/processed/with_cfa/samples.jsonl \ --output training/data/processed/cpg/ \ --workers 2 > logs/stage4_cpg.log 2>&1 & # Check cpg_stats.json after completion python -c " import json stats = json.load(open('training/data/processed/cpg/cpg_stats.json')) print('Success rate:', stats['success_rate_pct']) print('Avg DFG/CPG:', stats['avg_dfg_per_cpg']) print('Taint coverage:', stats['taint_coverage_pct']) assert float(stats['avg_dfg_per_cpg']) > 0, 'ZERO DFG EDGES!' assert float(stats['taint_coverage_pct']) >= 20, 'Taint coverage too low!' print('CHECKPOINT PASS')"

## 5.6 Production Issues for Stage 4

| Issue | Impact | Fix |
| --- | --- | --- |
| Joern cold-start ~12s/sample × 40K | ~134 hours sequential; 67 hours at 2 workers | 2 workers is the practical limit per 2GB JVM heap. Start Stage 4 FIRST on Day 3 — it runs while you build Stages 5–7. |
| Joern subprocess hangs on malformed C | Process blocks forever — checkpoint doesn't advance | subprocess.run with timeout=60. Catch TimeoutExpired. Log to cpg_failures.jsonl. Skip and continue. |
| JVM heap OOM with multiple workers | 2 workers × default JVM heap = OOM on machines < 8 GB RAM | Set _JAVA_OPTIONS=-Xmx2g in subprocess env. Max 2 workers on 8 GB machines. |
| GraphSON parse failure on empty export | Joern produces empty export.json for trivial 1-line functions | Check: if no export.json found in any subdir → log as failure, skip sample. |
| SARD samples still have #include custom headers after stage1 | Stage 1 doesn't strip ALL #include variants. Joern fails with 'cannot find header'. | SARD_STRIP_INCLUDES set handles the known ones. Add any newly discovered headers to this set. |
| Pair-aware discard runs too late | If Stage 4 crashes halfway, pair discard never runs → broken pairs enter Stage 5 | Add pair_aware_discard() as a standalone CLI flag too: --repair-pairs. Run it manually if Stage 4 was interrupted. |
| Windows: joern-parse.bat path issues | joern-parse.bat uses Unix-style paths internally. Windows paths with spaces cause errors. | Always use raw string paths and forward slashes. Wrap path in quotes inside subprocess command. |

# 6. Story P3-S5 — Stage 5: Node Embedding

| Item | Detail |
| --- | --- |
| File to build | training/scripts/preprocessing/stage5_embed.py (extend Phase 1 version) |
| Test file | tests/test_story_p3s5.py (extend test_story6.py) |
| Input | training/data/processed/cpg/{shard}/*.json |
| Output | training/data/processed/embedded/{shard}/{sample_id}.npz |
| Duration | ~27 min on Colab T4 GPU (190x faster than CPU). ~87 hours on CPU. |
| Depends on | Stage 4 complete. GPU available (see STORY6_COLAB_GUIDE.md). |
| Key rule | ALWAYS run on GPU. This stage is GPU-only in practice. |

## 6.1 Node Feature Vector (824-d)

| Range | Dimensions | Content | Source |
| --- | --- | --- | --- |
| [0:768] | 768 | CodeBERT [CLS] embedding of node code statement (max 64 tokens) | microsoft/codebert-base forward pass |
| [768:800] | 32 | Node type one-hot (17 Joern types + 15 reserved slots) | Joern node._label enum |
| [800:808] | 8 | Taint role one-hot: SOURCE/SINK/SANITIZER/PROPAGATION/NONE + 3 reserved | taint_analyzer from Stage 4 |
| [808:812] | 4 | CPG component membership: AST/CFG/DFG/TPG (4-d) | Assigned during CPG construction |
| [812:824] | 12 | Structural: in/out degree per type (6-d) + AST depth (2-d) + is_leaf + total_degree + BFS_dist_to_sink + has_taint_edge | Computed from edge list |

⚠ WARNING Empty code nodes MUST receive a zero vector for the CodeBERT region — do NOT skip them. They are structural CPG placeholders and removing them breaks the graph topology. batch_size=64 for CodeBERT inference is the optimum for T4 GPU. AMP (fp16) is enabled automatically on GPU.

## 6.2 Claude Code Prompt

▶ CLAUDE CODE PROMPT

Read training/scripts/preprocessing/stage5_embed.py from Phase 1 (Story 6). Read docs/STORY6_STAGE5_STAGE6.md for production results and known issues. Read docs/STORY6_COLAB_GUIDE.md for the Colab execution strategy. This story EXTENDS the Phase 1 Stage 5 implementation. Phase 1 processed ~34,691 CPGs. Phase 3 processes the FULL dataset including CFA samples. The code structure is largely complete — key additions needed: == CHANGE 1: Handle CFA samples distinctly == CFA samples (source ending in _cfa) have the same CPG structure as originals. No code changes needed — they process identically. Add to summary stats: count by source type (original vs cfa). == CHANGE 2: Verify 824-d shape strictly == Add assertion at save time: assert features.shape[1] == 824, f"Wrong feature dim: {features.shape}" This catches any upstream change to CPG structure immediately. == CHANGE 3: Add per-CWE embedding stats == After all samples embedded, compute and save: {cwe: {avg_taint_node_pct, avg_node_count, avg_dfg_degree}} per CWE Save to embedded/embed_stats_by_cwe.json == CHANGE 4: Detect and report node feature anomalies == After embedding each sample: if features.max() > 100: log warning (CodeBERT values shouldn't exceed ~15) if (features[:, 768:800].sum(axis=1) == 0).any(): log warning (some nodes have no type label) == COLAB NOTEBOOK UPDATE == The existing StreamGuard_Stage5_Stage6_Colab.ipynb covers this. Update Cell 4 (unzip) to handle the new with_cfa/ source directory structure. Update Cell 5b to process the larger dataset (target: 50K–80K CPG files). No other notebook changes needed. == CLI FLAGS (same as Phase 1) == --input (cpg dir), --output (embed dir), --device (cuda/cpu), --batch-size (default 64) --dry-run, --max-samples N, --verify == TESTS: tests/test_story_p3s5.py == Add 3 tests to existing test_story6.py: 1. Feature shape assertion triggers on wrong-shaped input 2. CFA sample (source='sard_cfa') embeds identically to structural equivalent 3. per-CWE stats file created with correct CWE keys

## 6.3 Colab Execution Guide

Stage 5 MUST run on GPU. Follow STORY6_COLAB_GUIDE.md exactly. Key steps:

- Zip training/data/processed/cpg/ locally → cpg_data.zip

- Upload cpg_data.zip to Google Drive: My Drive/StreamGuard/

- Open StreamGuard_Stage5_Stage6_Colab.ipynb in Colab

- Set Runtime to GPU (T4)

- Run all cells in order. Stage 5 takes ~27 min for 35K CPGs.

- Download embedded_data.zip and all_graphs.h5 from Drive

- Extract embedded_data.zip to training/data/processed/embedded/

- Copy all_graphs.h5 to training/data/graphs/all_graphs.h5

## 6.4 Checkpoint Verification

✓ CHECKPOINT # After downloading from Colab, verify locally: python -c " import numpy as np, glob files = list(glob.glob('training/data/processed/embedded/**/*.npz', recursive=True)) print('Total .npz files:', len(files)) # Sample 5 random files import random; sample = random.sample(files, min(5, len(files))) for f in sample: d = np.load(f) feat = d['features'] print(f'{f}: shape={feat.shape} dtype={feat.dtype} NaN={np.isnan(feat).any()} max={feat.max():.2f}') assert feat.shape[1] == 824, f'Wrong feature dim in {f}!' assert not np.isnan(feat).any(), f'NaN in {f}!' print('CHECKPOINT PASS')" # Target metrics: # All .npz files: shape (N, 824), float32, no NaN # Processing rate on Colab T4: ~21 samples/s # Total output size: ~3.1 GB for 35K samples

# 7. Story P3-S6 — Stage 6: Graph Tensors

| Item | Detail |
| --- | --- |
| File to build | training/scripts/preprocessing/stage6_graphs.py (extend Phase 1 version) |
| Test file | tests/test_story_p3s6.py (extend existing test_story6.py) |
| Input | training/data/processed/cpg/ + training/data/processed/embedded/ |
| Output | training/data/graphs/all_graphs.h5 |
| Duration | ~15 min for 35K samples (~42 graphs/s CPU) |
| Depends on | Stage 5 complete (all .npz files downloaded from Colab) |

## 7.1 HDF5 Schema

| Field | Shape | Dtype | Description |
| --- | --- | --- | --- |
| x | (num_nodes, 824) | float32 | Node features — 824-d vector from Stage 5 |
| edge_index | (2, num_edges) | int64 | COO format edge connectivity. Row 0 = src, Row 1 = dst. |
| edge_type | (num_edges,) | int32 | Edge type: AST=0, CFG=1, DFG=2, TPG=3. NO type >= 4. |
| y | scalar | int64 | Label: 0=safe, 1=vulnerable |
| attrs: cwe | string | — | CWE identifier e.g. CWE-120 |
| attrs: pair_id | string | — | CFA pair linkage UUID (empty string if unpaired) |
| attrs: source | string | — | Original collector source e.g. sard, cve |
| attrs: sample_id | string | — | UUID from schema |

## 7.2 Seven Validation Gates

Every graph must pass ALL seven gates before being written to the HDF5. Silent failures corrupt training.

| Gate | Check | Fail Action |
| --- | --- | --- |
| 1 | Trivial graph: num_nodes < 3 | Skip — log to graph_rejected.log |
| 2 | Feature shape mismatch: x.shape[1] != 824 | Skip — indicates Stage 5 error |
| 3 | NaN in features: np.isnan(x).any() | Skip — corrupts CodeBERT embeddings |
| 4 | Edge type out of range: any(edge_type >= 4) | Skip — would crash GGNN indexing |
| 5 | Edge index out of bounds: edge_index.max() >= num_nodes | Skip — CUDA will crash |
| 6 | Dangling edges: edge src/dst IDs not in node ID set | Skip — broken graph |
| 7 | No valid edges after filtering: len(edges) == 0 | Skip — trivially empty graph |

## 7.3 Claude Code Prompt

▶ CLAUDE CODE PROMPT

Read training/scripts/preprocessing/stage6_graphs.py from Phase 1. Read docs/STORY6_STAGE5_STAGE6.md §Stage 6 section. This story EXTENDS the Phase 1 Stage 6 implementation for the full dataset. The core implementation is complete from Phase 1. Key additions needed: == CHANGE 1: Add pair_id to HDF5 attrs == In the existing code, save pair_id as an HDF5 attribute on each sample group. grp.attrs['pair_id'] = sample.get('pair_id', '') This is CRITICAL — Stage 7 CFAAwareSplit needs pair_id to group pairs. == CHANGE 2: Validate pair_id linkage == After writing all graphs to HDF5, run a post-write check: Open HDF5 for reading. Build: pairs = {pair_id: [labels]} for all samples with non-empty pair_id. broken = {k: v for k,v in pairs.items() if 0 not in v or 1 not in v} If len(broken) > 0: log warning with count. These will be treated as singletons in Stage 7. == CHANGE 3: Per-CWE graph count in stats == In graph_stats.json, add: {cwe_distribution: {CWE-120: N, ...}} This lets Stage 7 split verify CWE coverage before training. == CHANGE 4: Contiguous node index remapping == Node IDs from Joern are Joern-internal integers (not 0-indexed). Remap to 0..N-1 before building edge_index: node_id_to_idx = {n['id']: i for i, n in enumerate(nodes)} edge_index = [[node_id_to_idx[e['src']], node_id_to_idx[e['dst']]] for e in edges if e['src'] in node_id_to_idx and e['dst'] in node_id_to_idx] == ALL SEVEN VALIDATION GATES must be implemented == See Section 7.2 above. Implement each as a separate check function. Log rejected graphs to graph_rejected.log with reason. == CLI FLAGS (same as Phase 1 + new flag) == --cpg-dir, --embed-dir, --output, --verify, --dry-run, --max-samples NEW: --check-pairs (run post-write pair integrity check) == TESTS: tests/test_story_p3s6.py == Add 4 tests to existing test_story6.py: 1. pair_id saved as HDF5 attribute and readable on reload 2. Contiguous node index remap: edge_index.max() < num_nodes after remap 3. Gate 4: edge_type=4 in input → graph rejected 4. Post-write pair check: broken pair logged as warning (not error)

## 7.4 Checkpoint Verification

✓ CHECKPOINT python training/scripts/preprocessing/stage6_graphs.py \ --cpg-dir training/data/processed/cpg/ \ --embed-dir training/data/processed/embedded/ \ --output training/data/graphs/all_graphs.h5 \ --check-pairs # Verify HDF5 python -c " import h5py, numpy as np with h5py.File('training/data/graphs/all_graphs.h5', 'r') as f: ids = list(f.keys()) print('Total graphs:', len(ids)) # Sample 5 import random; sample = random.sample(ids, min(5, len(ids))) for sid in sample: g = f[sid] x = g['x'][:] ei = g['edge_index'][:] et = g['edge_type'][:] y = int(g['y'][()]) pair_id = g.attrs.get('pair_id', '') print(f'{sid}: nodes={x.shape[0]} edges={ei.shape[1]} label={y} pair_id={pair_id[:8] if pair_id else "none"}') assert x.shape[1] == 824 assert ei.max() < x.shape[0], 'Edge index OOB!' assert et.max() < 4, 'Edge type >= 4!' assert not np.isnan(x).any(), 'NaN in features!' print('CHECKPOINT PASS')" # Expected: # Total graphs: 35,000–80,000 (depends on CFA ratio) # All edge_index: max < num_nodes # All edge_type: max < 4 # All features: no NaN

# 8. Story P3-S7 — Stage 7: CFA-Aware Split + Pre-Training Audit

| Item | Detail |
| --- | --- |
| Files to build | training/scripts/preprocessing/stage7_split.py + pre_training_audit.py |
| Test file | tests/test_story_p3s7.py |
| Input | training/data/graphs/all_graphs.h5 |
| Output | training/data/final/train.h5, val.h5, test.h5 |
| Duration | 10 min for split + 5 min for audit |
| Depends on | Stage 6 complete, all_graphs.h5 validated |
| Gate to Phase 4 | ALL 9 audit checks MUST PASS before any training run |

⛔ CRITICAL CFA pairs MUST stay together in the same split. A CFA pair split across train and test sets causes test data leakage. A pair split across train batches breaks the contrastive loss. The grouping order MUST be: pair_id > commit_sha > cve_id > singleton. Group FIRST, shuffle groups, THEN split.

## 8.1 Split Strategy

| Step | Action | Why |
| --- | --- | --- |
| 1 | Load all sample metadata from HDF5 (id, pair_id, commit_sha, cve_id, label, cwe) | Need grouping keys before splitting |
| 2 | Build split groups: pair_id > commit_sha > cve_id > singleton | Ensures same real-world bug stays in same split |
| 3 | Shuffle GROUPS with seed=42 (not individual samples) | Reproducibility. Never shuffle individuals. |
| 4 | Split groups 80/10/10 on group count | Group-based split — not sample-based |
| 5 | Assert zero commit_sha overlap between train and test | Prevents data leakage from multi-source collection |
| 6 | Assert zero pair_id overlap between splits | No CFA pair member can be in two splits |
| 7 | Write train.h5, val.h5, test.h5 | Copy graphs from all_graphs.h5 to split files |

## 8.2 Pre-Training Audit — 9 Mandatory Checks

| Check | Condition | M1 Threshold | M2 Full Threshold | Fail Action |
| --- | --- | --- | --- | --- |
| 1: min_train_samples | Training set size | >= 5,000 | >= 30,000 | Collect more data |
| 2: vuln_safe_balance | label=1 percentage in train | (0.40, 0.60) | (0.45, 0.55) | Weight loss or resample |
| 3: cwe_diversity | CWEs with >= 500 samples | >= 5 | >= 7 | Collect underrepresented CWEs |
| 4: max_cwe_dominance | Max fraction from one CWE | <= 0.45 | <= 0.40 | Downsample dominant CWE |
| 5: no_null_code | Samples with empty code | == 0 | == 0 | Fix upstream collector |
| 6: test_train_no_overlap | Shared commit SHAs train/test | == 0 | == 0 | Re-split with correct grouping |
| 7: code_length_range | Token count in [10, 4096] | All pass | All pass | Stage 1 filter missed some |
| 8: pair_integrity | Broken CFA pairs | == 0 | == 0 | Run repair_broken_pairs() |
| 9: min_taint_coverage | % samples with >= 1 taint node | >= 0.20 | >= 0.25 | Expand SOURCES/SINKS in Stage 4 |

## 8.3 Claude Code Prompt

▶ CLAUDE CODE PROMPT

Read docs/PREPROCESSING.md §Stage 7 and §Pre-Training Validation completely. Read training/scripts/model/cfa_dataloader.py (Phase 1) to understand how pair_id is used during training. BUILD FILE 1: training/scripts/preprocessing/stage7_split.py == FUNCTION: build_split_groups(metadata: list[dict]) -> dict == Priority order for grouping: key = m.get("pair_id") or m.get("commit_sha") or m.get("cve_id") or m["sample_id"] groups = {} for m in metadata: groups.setdefault(key, []).append(m["sample_id"]) return groups == FUNCTION: split_groups(groups: dict, ratios=(0.8, 0.1, 0.1), seed=42) -> tuple == import random; random.seed(42) group_keys = list(groups.keys()) random.shuffle(group_keys) n = len(group_keys) n_train = int(n * ratios[0]) n_val = int(n * ratios[1]) train_keys = group_keys[:n_train] val_keys = group_keys[n_train:n_train+n_val] test_keys = group_keys[n_train+n_val:] train_ids = [sid for k in train_keys for sid in groups[k]] val_ids = [sid for k in val_keys for sid in groups[k]] test_ids = [sid for k in test_keys for sid in groups[k]] return train_ids, val_ids, test_ids == VALIDATION ASSERTIONS (run before writing) == # Assert no pair_id split for split_name, ids in [("train", train_ids), ("val", val_ids), ("test", test_ids)]: pair_ids_in_split = set(m["pair_id"] for m in metadata if m["sample_id"] in set(ids) and m.get("pair_id")) for other_name, other_ids in [("val", val_ids), ("test", test_ids)]: pair_ids_in_other = set(m["pair_id"] for m in metadata if m["sample_id"] in set(other_ids) and m.get("pair_id")) overlap = pair_ids_in_split & pair_ids_in_other assert len(overlap) == 0, f"Pair ID overlap between train and {other_name}: {len(overlap)} pairs" # Assert no commit SHA leakage train_shas = set(m["commit_sha"] for m in metadata if m["sample_id"] in set(train_ids) and m.get("commit_sha")) test_shas = set(m["commit_sha"] for m in metadata if m["sample_id"] in set(test_ids) and m.get("commit_sha")) overlap = train_shas & test_shas assert len(overlap) == 0, f"Commit SHA overlap train/test: {len(overlap)} SHAs" == FUNCTION: write_split_h5(source_h5, split_ids, output_path) == Open source_h5 for reading. Open output_path for writing. Copy each graph in split_ids from source to output. Preserve all attrs (pair_id, cwe, source, sample_id). == CLI FLAGS == --input, --output-dir (default training/data/final/), --seed (default 42), --dry-run BUILD FILE 2: training/scripts/preprocessing/pre_training_audit.py == REQUIRED_CHECKS dict == REQUIRED_CHECKS_M1 = { "min_train_samples": 5_000, "vuln_safe_balance": (0.40, 0.60), "cwe_diversity": 5, "max_cwe_dominance": 0.45, "no_null_code": 0, "test_train_no_overlap": 0, "code_length_range": (10, 4096), "pair_integrity": 0, "min_taint_coverage": 0.20, } REQUIRED_CHECKS_M2 = { # Use for full dataset "min_train_samples": 30_000, "vuln_safe_balance": (0.45, 0.55), "cwe_diversity": 7, "max_cwe_dominance": 0.40, "no_null_code": 0, "test_train_no_overlap": 0, "code_length_range": (10, 4096), "pair_integrity": 0, "min_taint_coverage": 0.25, } == Each check is a function returning (passed: bool, message: str) == Run all 9 checks. Print table: check_name ¦ PASS/FAIL ¦ detail. If ALL pass: exit(0) and print "PRE-TRAINING AUDIT PASSED — Safe to begin training." If ANY fail: exit(1) and print "PRE-TRAINING AUDIT FAILED — Fix before training." == CLI FLAGS == --dataset (path to final/ dir), --m1 (use M1 thresholds), --m2 (use M2 thresholds, default) --fix-pairs (run repair_broken_pairs before checking) == TESTS: tests/test_story_p3s7.py — 12 tests == 1. build_split_groups: pair_id takes priority over singleton 2. build_split_groups: commit_sha used when no pair_id 3. split_groups: ratios produce correct proportions 4. split_groups: seed=42 gives reproducible result 5. Pair integrity assertion: pair split across train/test → AssertionError 6. SHA overlap assertion: commit_sha in both train and test → AssertionError 7. Audit check 1: train < 5000 → FAIL 8. Audit check 2: label balance 30/70 → FAIL 9. Audit check 6: SHA overlap → FAIL 10. Audit check 8: broken pair → FAIL 11. Audit ALL pass → exit code 0 12. Audit ANY fail → exit code 1

## 8.4 Checkpoint Verification

✓ CHECKPOINT # Run Stage 7 split python training/scripts/preprocessing/stage7_split.py \ --input training/data/graphs/all_graphs.h5 \ --output-dir training/data/final/ # Verify splits python -c " import h5py for split in ['train', 'val', 'test']: with h5py.File(f'training/data/final/{split}.h5', 'r') as f: ids = list(f.keys()) labels = [int(f[sid]['y'][()]) for sid in ids] pair_ids = set(f[sid].attrs.get('pair_id','') for sid in ids if f[sid].attrs.get('pair_id','')) print(f'{split}: N={len(ids)} label1={sum(labels)} label0={len(labels)-sum(labels)} pairs={len(pair_ids)}') # Verify zero SHA overlap from collections import defaultdict import h5py shas = defaultdict(set) for split in ['train', 'val', 'test']: with h5py.File(f'training/data/final/{split}.h5', 'r') as f: for sid in f.keys(): sha = f[sid].attrs.get('commit_sha','') if sha: shas[split].add(sha) overlap = shas['train'] & shas['test'] print('train/test SHA overlap:', len(overlap)) assert len(overlap) == 0, 'DATA LEAKAGE!' print('SPLIT CHECKPOINT PASS')" # Run pre-training audit python training/scripts/preprocessing/pre_training_audit.py \ --dataset training/data/final/ --m2 # ALL 9 checks must print PASS # If any FAIL: fix before starting Phase 4 training

## 8.5 Production Issues for Stage 7

| Issue | Impact | Fix |
| --- | --- | --- |
| Pair_id not set for singleton SARD samples | build_split_groups falls back to sample_id as key — correct, but doesn't guarantee CFA pair stays together | This is correct behavior. Singletons (pair_id='') are treated independently. Only CFA pairs need group-level protection. |
| CWE diversity check fails on M2 threshold | Phase 2 API collectors incomplete — only 5 CWEs have >= 500 samples | Use --m1 flag for now. Run remaining API collectors. Rerun audit with --m2 when collection is complete. |
| Label imbalance after CFA augmentation | CFA generation created 3× more label=0 (safe) samples than label=1 (vulnerable) — balance check fails | CFA pairs ADD label=0 counterparts to label=1 originals. Expected: after CFA, label=0 increases. Adjust vuln_safe_balance threshold to (0.30, 0.60) for M1. |
| taint_coverage check fails below 20% | Juliet good() functions have very few taint paths — they ARE the fixed versions | This is expected for SARD. The 0.20 M1 threshold already accounts for this. If still failing: check taint labeling in Stage 4. |
| SHA overlap persists after grouping | OSV and CVE collected same commit despite Phase 2 cross-dedup | Re-run Stage 2 dedup specifically for SHA overlap. Then re-run Stage 6 and Stage 7. |

# 9. Day-by-Day Execution Timeline

Phase 3 runs over 7–14 calendar days. Stage 4 (Joern CPG) is the bottleneck. Start it as early as possible.

| Day | Foreground Task | Background Task | Milestone |
| --- | --- | --- | --- |
| Day 1 | Build + test P3-S1 (Stage 1 Clean) | Start Stage 1 on SARD+ExploitDB data | cleaned/samples.jsonl ready |
| Day 1 | Build + test P3-S2 (Stage 2 Dedup) | Run Stage 2 immediately after Stage 1 | deduped/samples.jsonl ready |
| Day 2 | Build + test P3-S3 (Stage 3 CFA) | Start CFA generation in background (will take 22+ hours) | CFA running, first 1K CFAs generated |
| Day 3 | Build + test P3-S4 (Stage 4 CPG) | START STAGE 4 ON ALREADY-CLEANED DATA. This is the bottleneck — start immediately. | Stage 4 running in background |
| Day 4–7 | Monitor Stage 4 progress | Stage 4 continues (3–4 days). Fix any per-sample failures. | ~10K CPGs/day at 2 workers |
| Day 7 | Build + test P3-S5 (Stage 5 Embed) | Prepare cpg_data.zip for Colab upload | cpg_data.zip ready |
| Day 7–8 | Upload to Colab + run Stage 5 GPU | Stage 5 on Colab T4: ~27 min for 35K CPGs | embedded_data.zip ready |
| Day 8 | Download from Colab + build P3-S6 (Stage 6) | Run Stage 6 locally (~15 min) | all_graphs.h5 ready |
| Day 9 | Build + run P3-S7 (Stage 7 Split + Audit) | Run pre_training_audit.py | PHASE 3 COMPLETE — ready for Phase 4 |

✔ TIP / NOTE Do not wait for Stage 3 (CFA generation) to complete before starting Stage 4 (CPG construction). Stage 4 can run on all samples that have already passed Stage 2, including SARD native pairs. When Stage 3 finishes, merge the with_cfa samples into the CPG queue.

## 9.1 Quick Reference — All Files

| File | Directory | Purpose |
| --- | --- | --- |
| stage1_clean.py | training/scripts/preprocessing/ | Clean & normalize C functions |
| stage2_dedup.py | training/scripts/preprocessing/ | 4-level deduplication |
| stage3_cfa.py | training/scripts/preprocessing/ | LLM counterfactual augmentation |
| stage4_cpg.py | training/scripts/preprocessing/ | Joern CPG construction + TPG |
| generate_cpg.sc | training/scripts/preprocessing/joern_scripts/ | Joern Scala script |
| stage5_embed.py | training/scripts/preprocessing/ | CodeBERT node embedding (GPU) |
| stage6_graphs.py | training/scripts/preprocessing/ | PyG Data + HDF5 assembly |
| stage7_split.py | training/scripts/preprocessing/ | CFA-aware train/val/test split |
| pre_training_audit.py | training/scripts/preprocessing/ | 9-check quality gate |
| StreamGuard_Stage5_Stage6_Colab.ipynb | repo root | Colab notebook for GPU embedding |

# 10. Production Issues Review

This section documents all production-level issues found across the full Phase 3 plan. 18 issues total: 5 Critical, 7 High, 4 Medium, 2 Low.

| # | Issue | Stage(s) | Severity | Mitigation Status |
| --- | --- | --- | --- | --- |
| PI-01 | tree-sitter 0.22+ API breaking change — Language.build_library() removed | S1 | HIGH | Fix in P3-S1 |
| PI-02 | SARD #ifdef stripping not done before comment removal — Joern sees incomplete CPG | S1, S4 | CRITICAL | Fix in P3-S1 |
| PI-03 | MinHash L4 removes one side of SARD CFA pair — broken pair enters Stage 4 | S2 | CRITICAL | Fix in P3-S2 (repair_broken_pairs) |
| PI-04 | Short SHA mismatch between sources — L3 dedup misses cross-source duplicates | S2 | HIGH | SHA normalization from Phase 2; L4 catches residuals |
| PI-05 | LLM returns explanation text before code — extract_c_code misses the function | S3 | HIGH | Robust extract_c_code with fallback |
| PI-06 | gcc not available on Windows — Gate 3 crashes for every CFA generation | S3 | HIGH | Check shutil.which('gcc'); skip Gate 3 with warning if absent |
| PI-07 | SARD native CFA pairs re-processed by Stage 3 — pair_id overwritten | S3 | CRITICAL | Skip CFA generation for samples with cfa_type='native' or source='sard' |
| PI-08 | Stage 3 output JSONL grows to multi-GB — resume reads whole file on restart | S3 | MEDIUM | Checkpoint by processed sample IDs (not re-reading output JSONL) |
| PI-09 | DFG edges = 0 after Joern CPG construction — GGNN has no data flow signal | S4 | CRITICAL | Verify DFG in first 5 CPGs before full run. In Joern 4.x CLI, DFG included by default. |
| PI-10 | CDG edges stored as type 4 — CUDA index-out-of-bounds crash during training | S4, S6 | CRITICAL | Drop all edges not in EDGE_TYPE_MAP. Assert edge_type.max() < 4. |
| PI-11 | Joern subprocess hangs on malformed C function — no timeout | S4 | HIGH | subprocess.run with timeout=60. Catch TimeoutExpired. Log to failures. |
| PI-12 | JVM OOM with >2 workers on 8GB machine | S4 | MEDIUM | Set _JAVA_OPTIONS=-Xmx2g. Hard limit: 2 workers per 8 GB RAM. |
| PI-13 | Stage 5 run on CPU: 87 hours vs 27 min on GPU | S5 | HIGH | MANDATORY: Run Stage 5 on Colab T4 GPU. Document in story prominently. |
| PI-14 | Empty code nodes skipped — breaks graph topology | S5 | HIGH | Empty code nodes MUST receive zero vector. Never skip. |
| PI-15 | pair_id not saved in HDF5 attrs — Stage 7 cannot group pairs | S6 | CRITICAL (if missed) | Explicitly save pair_id as HDF5 attribute in Stage 6. |
| PI-16 | Edge index not remapped to 0..N-1 — edge_index.max() >= num_nodes | S6 | HIGH | node_id_to_idx remapping MANDATORY before building edge_index. |
| PI-17 | CWE diversity audit fails — API collectors not yet complete | S7 | MEDIUM | Use --m1 flag for Phase 1 proof. Re-run with --m2 after full collection. |
| PI-18 | SHA overlap not caught if same commit has short+full SHA variants in different collectors | S7 | MEDIUM | Normalize all SHAs to 40 chars in Stage 2 before L3 check. |

## 10.1 Critical Issues — Full Detail

### PI-02: SARD #ifdef Stripping MUST Happen Before Comment Removal

Juliet C files wrap functions in #ifndef OMITBAD / #ifndef OMITGOOD preprocessor guards. If comment removal runs first, the #ifdef lines remain in the code. When Joern processes this in Stage 4, it sees conditional compilation directives and produces a CPG for the WRONG code path — or an empty CPG if the guard prevents compilation.

- Fix: In normalize(), call strip_preprocessor_guards() FIRST, before any comment removal

- Add test: verify stripped code does not contain any #ifdef/#ifndef/#endif

- Verify: Stage 4 CPGs for SARD samples have > 3 nodes

### PI-03: MinHash May Break SARD CFA Pairs

Juliet's good() variants (goodG2B1, goodG2B2, goodG2B3) are structurally near-identical functions that differ only in one integer or string literal. MinHash at 0.85 Jaccard threshold may keep goodG2B1 and remove goodG2B2. If goodG2B1 and bad() shared a pair_id, and goodG2B2 was the paired sample for another pair, the bad() partner is now orphaned.

- Fix: repair_broken_pairs() MUST run after every dedup level, not just at the end

- Add test: deliberately create a near-dup pair; verify repair clears orphan's pair_id

### PI-07: Stage 3 Must Not Regenerate CFAs for SARD

SARD's _bad.c and _good.c files ARE native CFA pairs — process_sard.py already assigned pair_id to link them. If Stage 3 runs LLM CFA generation on SARD vulnerable samples, it will: (1) generate a NEW LLM counterpart, (2) assign a NEW pair_id, overwriting the original native pair linkage, and (3) break the original native pair that was already valid.

- Fix: if sample.get('cfa_type') == 'native' OR sample['source'] in {'sard', 'sard_cfa'}: skip CFA generation

- Only generate LLM CFAs for: exploitdb, cve, github_advisory, osv, repo sources

### PI-09: DFG Zero Edges = Complete GGNN Failure

Without DFG edges, the GGNN cannot propagate data flow information. CWE-89 (SQL injection), CWE-78 (OS command injection), and CWE-134 (format string) detection all depend critically on tracking how untrusted user input propagates to dangerous sinks. A GNN without DFG will achieve ~0.70 F1 maximum — far below the 0.92 target.

- Early detection: after processing first 5 samples, check dfg_edges > 0 on each

- Joern 4.x CLI: joern-parse includes DFG by default. REPL mode: run.ossdataflow required.

- If DFG is zero: STOP all processing. Fix Joern setup. Do not waste 4 days building CPGs without DFG.

### PI-15: pair_id in HDF5 is Critical for CFA Training

The CFAAwareBatchSampler in training (Phase 4) groups batches by pair_id to keep CFA pairs together. If pair_id is not saved in the HDF5, the sampler treats every sample as a singleton. The contrastive loss L_CFA then trains on RANDOM pairs instead of (vulnerable, safe) CFA pairs — completely invalidating the research contribution.

- Fix: grp.attrs['pair_id'] = sample.get('pair_id', '') in Stage 6 write loop

- Verify: h5py read pair_id attrs for 10 samples that should have pair_ids. Assert non-empty.

## 10.2 Go / No-Go Decision Criteria

These are hard gates. If any condition is not met, do NOT proceed to Phase 4 training.

| Gate | Condition | Check Command | If FAIL |
| --- | --- | --- | --- |
| Before Stage 4 | DFG edges > 0 in first 5 CPGs | grep dfg_edges cpg_stats.json ¦ check > 0 | Fix Joern setup. Do NOT continue. |
| Before Stage 5 | All Stage 4 CPGs have >= 3 nodes | validate_graphs.py --min-nodes 3 | Re-run Stage 4 on failed samples. |
| Before Stage 6 | All .npz files: shape (N, 824), no NaN | stage5_embed.py --verify | Re-run Stage 5 on failed samples. |
| Before Stage 7 | edge_index.max() < num_nodes in all graphs | stage6_graphs.py --verify | Stage 6 gate 5 should have caught these. |
| Before Phase 4 | pre_training_audit.py: all 9 checks PASS | python pre_training_audit.py --m2 | Fix each failing check before training. |
| Before Phase 4 | Zero pair_id overlap between train and test | Stage 7 assertion in split code | Re-split with correct grouping logic. |
| Before Phase 4 | Zero commit SHA overlap train/test | Stage 7 assertion in split code | Re-split. Check Phase 2 cross-dedup. |

## 10.3 Environment Variable Checklist

| Variable | Used By | Required From | Verify Command |
| --- | --- | --- | --- |
| ANTHROPIC_API_KEY | Stage 3 CFA generation | Day 2 (Stage 3 start) | python -c "from anthropic import Anthropic; c=Anthropic(); print('OK')" |
| JOERN_BIN | Stage 4 CPG construction | Day 3 (Stage 4 start) | echo $JOERN_BIN && $JOERN_BIN --version |
| JOERN_EXPORT | Stage 4 CPG export | Day 3 (Stage 4 start) | echo $JOERN_EXPORT |
| STREAMGUARD_DATA_DIR | All stages | All days | echo $STREAMGUARD_DATA_DIR && df -h $STREAMGUARD_DATA_DIR |
| _JAVA_OPTIONS | Stage 4 JVM heap | Day 3 | export _JAVA_OPTIONS="-Xmx2g" |

## 10.4 Summary — Phase 3 Completion Criteria

Phase 3 is complete when ALL of the following are true:

- Stage 1: cleaned/samples.jsonl exists, no #ifdef in any code field

- Stage 2: deduped/samples.jsonl exists, 0 broken pairs, realistic dedup reduction

- Stage 3: with_cfa/samples.jsonl exists, compile_rate >= 80%, pattern_removal >= 60%

- Stage 4: cpg/ directory has >= 30K .json files, avg_dfg_per_cpg > 0, taint_coverage >= 20%

- Stage 5: embedded/ directory has matching .npz files, all (N, 824) float32, no NaN

- Stage 6: all_graphs.h5 exists, all edge_index bounds valid, pair_id attrs populated

- Stage 7: train.h5, val.h5, test.h5 created, 0 SHA overlap train/test, 0 broken pairs

- Audit: pre_training_audit.py prints ALL 9 PASS — safe to begin Phase 4 training

StreamGuard Phase 3 — Preprocessing Pipeline | v1.0 | March 2026