StreamGuard

Phase 2 — Full Data Collection

Risk Analysis Document

What Can Go Wrong, How Bad It Is, and What You Must Do About It

| Version | 1.0 — March 2026 |
| --- | --- |
| Status | ACTIVE — Read before starting any collector |
| Audience | Implementer (you + Claude Code) |
| Risks Catalogued | 27 total: 6 Critical, 9 High, 8 Medium, 4 Low |
| Tone | Blunt. No sugar-coating. |
| Objective | Build a dataset good enough for a top-venue paper. Nothing less. |

# 1. Executive Summary — The Blunt Version

⚑ BLUNT REALITY — Read This Before You Write a Single Line of Code Phase 2 is not the exciting part. The model is the exciting part. But if Phase 2 fails, there is no model. Bad data does not produce a bad paper — it produces no paper. The risks in this document are not edge cases. They are things that WILL happen during a 10-day background collection run across 6 sources and 5 API systems. Some will happen on Day 1. The question is whether you catch them in 10 minutes or 5 days. This document is organized by what will kill the project (Critical), what will waste a week (High), what will quietly degrade your results (Medium), and what is annoying but fixable (Low). Read all of it. Implement all mitigations before you start.

| Category | Description | Risk Count | Worst Case If Ignored |
| --- | --- | --- | --- |
| CRITICAL | Project-killing risks — collection produces nothing or garbage | 6 | Restarting from scratch. Weeks lost. |
| HIGH | Research-invalidating risks — data collected but paper claims don't hold | 9 | Reviewers reject on experimental grounds. Results irreproducible. |
| MEDIUM | Quality-degrading risks — data works but model underperforms | 8 | F1 targets missed. Ablations inconclusive. |
| LOW | Operational friction — slows collection or causes minor rework | 4 | 1–2 days of cleanup work. |

● The Single Most Important Sentence in This Document A training dataset that looks clean in a naive line-count check can still completely invalidate your research results through test set contamination, label noise, or CWE distribution collapse — and you will not discover this until AFTER training. The pre_training_audit.py script is not optional. The post-collection audit is not optional. Every checkpoint in the Stories document is not optional.

# 2. Full Risk Register

All 27 risks catalogued. Probability = likelihood of occurring during Phase 2. Impact = consequence for the project. Mitigation Status as of document date.

| ID | Risk Title | Category | Severity | Prob. | Impact | Mit. Status |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Test set contamination via shared commit SHA | Research Validity | CRITICAL | HIGH | CRITICAL | PARTIAL |
| R-02 | CWE-4 coverage collapse (CWE-89/79/125/119 near-zero) | Data Quality | CRITICAL | HIGH | CRITICAL | PARTIAL |
| R-03 | Broken CFA pairs enter training — contrastive loss corrupted | Data Integrity | CRITICAL | MEDIUM | HIGH | PARTIAL |
| R-04 | Label noise from incorrect CVE→CWE mapping | Data Quality | CRITICAL | HIGH | HIGH | DONE |
| R-05 | Duplicate functions across sources inflate apparent dataset size | Data Quality | CRITICAL | HIGH | HIGH | PARTIAL |
| R-06 | NVD API v1.0 used — silently returns zero samples | API/Collection | CRITICAL | MEDIUM | CRITICAL | DONE |
| R-07 | GitHub token missing/expired — 60 req/hr instead of 5000 | API/Collection | HIGH | MEDIUM | HIGH | DONE |
| R-08 | GraphQL cursor expiry — collection halts with no recovery | API/Collection | HIGH | HIGH | HIGH | DONE |
| R-09 | Repo Miner keyword filter too broad — abuse detection triggered | API/Collection | HIGH | HIGH | HIGH | DONE |
| R-10 | ExploitDB CWE assignment is random guessing without inference map | Data Quality | HIGH | HIGH | HIGH | DONE |
| R-11 | ExploitDB rule-based mutations produce invalid C — corrupt CFA pairs | Data Integrity | HIGH | MEDIUM | MEDIUM | DONE |
| R-12 | SARD CWE distribution: CWE-416 and CWE-476 under 2% each | Data Quality | HIGH | CERTAIN | MEDIUM | PARTIAL |
| R-13 | Disk space exhaustion mid-collection — partial JSONL = corrupt data | Infrastructure | HIGH | MEDIUM | HIGH | DONE |
| R-14 | Checkpoint corruption on kill -9 — collection restarts from zero | Infrastructure | HIGH | MEDIUM | HIGH | DONE |
| R-15 | HTTP 503 from NVD treated as permanent failure — no retry | API/Collection | HIGH | HIGH | HIGH | DONE |
| R-16 | Short SHA vs full SHA mismatch — same commit collected twice | Data Quality | MEDIUM | HIGH | MEDIUM | DONE |
| R-17 | GitHub secondary rate limit (abuse) — 403 not handled | API/Collection | MEDIUM | MEDIUM | MEDIUM | DONE |
| R-18 | BaseCollector hash load O(n) — 60s+ restart on 18K+ samples | Performance | MEDIUM | MEDIUM | LOW | DONE |
| R-19 | Function extraction failing on C macros — silent sample loss | Data Quality | MEDIUM | HIGH | MEDIUM | PARTIAL |
| R-20 | CWE inference from commit message is wrong 15–25% of the time | Data Quality | MEDIUM | HIGH | MEDIUM | PARTIAL |
| R-21 | SARD label=0 dominates final dataset (58%) — imbalance risk | Data Quality | MEDIUM | CERTAIN | LOW | PARTIAL |
| R-22 | ExploitDB clone from GitLab fails behind corporate proxy | Infrastructure | MEDIUM | LOW | MEDIUM | PARTIAL |
| R-23 | OSV pagination page token not saved — restart from page 1 | API/Collection | MEDIUM | MEDIUM | LOW | DONE |
| R-24 | Windows path with '(1)' breaks CLI argument parsing | Infrastructure | LOW | HIGH | LOW | DONE |
| R-25 | chardet fallback to latin-1 corrupts multi-byte C comments | Data Quality | LOW | MEDIUM | LOW | PARTIAL |
| R-26 | Repo Miner torvalds/linux: 3000+ commits, 30+ hours | Performance | LOW | CERTAIN | LOW | PARTIAL |
| R-27 | MLflow not running when collector finishes — stats lost | Observability | LOW | LOW | LOW | PARTIAL |

Prob. scale: CERTAIN=90%+, HIGH=60-90%, MEDIUM=30-60%, LOW=<30%.  Impact: CRITICAL=project-ending, HIGH=week of rework, MEDIUM=degraded results, LOW=hours of cleanup.

# 3. Critical Risks — Full Detail

These six risks will destroy the validity of the paper or require starting over. Every mitigation must be implemented before collection begins.

## R-01 — Test Set Contamination via Shared Commit SHA

⚑ BLUNT REALITY — This is the single most dangerous risk in the entire project The ICSE 2025 paper by Ding et al. — which this project cites — proved that virtually every major vulnerability dataset has massive test/train contamination from duplicate functions. StreamGuard is collecting from 6 sources that ALL reference GitHub commits. The same CVE fix commit can appear in: NVD collector, GitHub Advisory, OSV, AND Repo Miner. If any of those four collectors give the same commit to both train and test splits: your F1 numbers are inflated, your ablation results are wrong, and reviewers will catch it.

▲ RISK — Cross-source commit SHA leakage into test set Without commit SHA cross-dedup, the same before/after code pair will appear in both train and test. Stage 7 split groups by pair_id — but pair_ids differ across collectors even for the same commit. Result: model memorises the specific code pattern → inflated test F1 that disappears in deployment. ICSE 2025 found duplication rates of 40–80% in popular vulnerability datasets. StreamGuard is not immune.

→ MITIGATION — Three-layer deduplication system Layer 1 — WITHIN each collector: MD5 hash of whitespace-normalised code (BaseCollector). Layer 2 — ACROSS collectors: full 40-char commit SHA cross-dedup (OSV loads CVE SHAs, Repo Miner loads both). Layer 3 — Stage 2 MinHash LSH (Jaccard ≥ 0.85) — catches functionally-identical code with different whitespace. Stage 7 split: groups by pair_id > commit_sha > cve_id — never splits the same real-world bug across train/test. Post-collection audit R-01 check: assert zero overlap between train commit_sha set and test commit_sha set. If this assertion fails: full re-split required before ANY training run. Do not skip this check.

## R-02 — CWE Coverage Collapse for 4 Target CWEs

⚑ BLUNT REALITY — SARD doesn't have 5 of your 12 target CWEs. This is a known gap. SARD (Juliet v1.3.1) covers: CWE-78, CWE-121, CWE-122, CWE-134, CWE-190, CWE-416, CWE-476. SARD does NOT have: CWE-89, CWE-79, CWE-119, CWE-125. Your paper claims per-CWE F1 ≥ 0.88 on all 12 types. Without API sources, 4 CWEs will have near-zero training data. The model will not learn them. The paper claim will be false. Current status of API collection: CWE-89 (SQL Injection): comes from CVE + GitHub Advisory only. CWE-79 (XSS in C): comes from CVE + GitHub Advisory only. C web servers are rare. CWE-119 (General Buffer): comes from CVE + Repo Miner. CWE-125 (Out-of-Bounds Read): comes from Linux kernel commits. Repo Miner only.

▲ RISK — Training data imbalance invalidates per-CWE F1 claims If CWE-89 has 80 training samples vs CWE-120 with 9,000: per-CWE F1 for CWE-89 is noise. PRD requirement: each CWE needs ≥ 500 samples for meaningful metrics. If API collection is incomplete (cancelled early, rate-limited too aggressively), 4 CWEs will be sparse. The paper's per-CWE F1 table becomes dishonest for underrepresented classes.

→ MITIGATION — CWE-specific monitoring + targeted supplementation Run CWE count check after every 24 hours of collection: python3 -c "[CWE distribution check]" Threshold: flag any CWE with < 500 samples after all collectors have run. If CWE-89 < 500 after CVE + GitHub Advisory complete: run a targeted NVD query for CWE-89 specifically. Worst case fallback: Use Anthropic Claude to generate synthetic CWE-89 C functions as SARD-style pairs. This is not ideal — label it source='manual' and reviewer_verified=False in the schema. Report distribution honestly in the paper: 'CWE-79 is underrepresented (N=X) due to limited C web server CVEs.' Do not hide the imbalance. Reviewers check. If you hide it and they find it, the paper is rejected.

## R-03 — Broken CFA Pairs Corrupt Contrastive Training

⚑ BLUNT REALITY — A broken CFA pair is worse than no CFA pair at all The entire research claim rests on contrastive loss L_CFA pushing vulnerable/safe embeddings apart. L_CFA assumes: emb_v is label=1, emb_v' is label=0, and they are structurally identical except for the fix. A broken pair — where pair_id links two label=1 samples, or two unrelated functions — makes the contrastive loss ACTIVELY HARMFUL. It pushes embeddings of the wrong things apart. The model will train to 'convergence' on wrong objectives. F1 will be lower than the baseline. The paper's core claim (CFA improves F1) will appear to be false. This has happened in prior work.

▲ RISK — Sources of broken pairs Source 1 — Collector bug: same pair_id assigned to two label=1 samples. Source 2 — Validation failure: one side of a pair fails validate_sample() and is dropped silently. Source 3 — ExploitDB mutation failure: mutation produces invalid C, gcc rejects it, pair dropped but original retains pair_id. Source 4 — Stage 1 clean filter: one side falls below 5-line minimum after #ifdef stripping. Source 5 — Stage 2 dedup: MinHash removes one side as near-duplicate of a different sample.

→ MITIGATION — Four-layer pair integrity system Layer 1 — Inline validation in BaseCollector: finalize_pairs() clears orphaned pair_ids before any sample leaves the collector. Layer 2 — Post-collection audit CHECK 5: assert zero broken pairs in merged JSONL. This is a FAIL condition. Layer 3 — Stage 2: after dedup, re-run pair integrity check. If a dedup operation breaks a pair, discard both. Layer 4 — Stage 7: CFAAwareBatchSampler's __init__ validates that every pair_id has exactly 2 samples (0 and 1). If a pair breaks at Stage 7: log it, set pair_id='' on the orphan, continue. Never crash training over a single broken pair. Target: zero broken pairs entering training. Accept reality: < 0.1% broken pairs after all layers is acceptable.

## R-04 — Label Noise from Incorrect CVE→CWE Mapping

⚑ BLUNT REALITY — NVD's CWE assignments are wrong 20–30% of the time. This is documented. NVD assigns CWEs from vendor-submitted CVEs. Vendors often choose the broadest applicable CWE (CWE-119: Buffer Errors) rather than the specific one (CWE-120 or CWE-121). Researchers have measured NVD CWE error rates at 20–40% in published studies. If you accept NVD CWE labels blindly: your 12-class CWE head will train on noisy labels. CWE-119 will be massively overrepresented. CWE-121 and CWE-122 will be underrepresented. Per-CWE F1 metrics will be meaningless. The CWE-head Top-1 accuracy target (≥ 0.82) will fail.

→ MITIGATION — Four-tier CWE assignment with explicit confidence scores Tier 1 — Direct CWE from source (highest confidence): NVD entry has exactly one CWE in VALID_CWE set. Tier 2 — Code-based inference: keyword match on function code (specific patterns like 'gets(' → CWE-120). Tier 3 — Commit message inference: keyword scoring on commit message text. Tier 4 — Description inference: NLP keyword match on CVE description. Lowest confidence. Store: cwe_confidence: {source: 'nvd_direct' ¦ 'code_inferred' ¦ 'commit_inferred' ¦ 'desc_inferred'} During training: use label_smoothing=0.2 for Tier 3 and Tier 4 samples on the CWE head. During evaluation: report per-CWE F1 separately for Tier 1 samples only. This is your honest metric. Flag in paper: 'CWE labels for API sources use Tier 1-2 assignment; noisy labels smoothed during training.'

## R-05 — Duplicate Functions Inflate Dataset Size

⚑ BLUNT REALITY — You will not have 50K unique functions. You will have far fewer. SARD's Juliet suite is synthetically generated. Many 'different' test cases differ only in the variable name or constant value. goodG2B1() and goodG2B2() are structurally identical except for one integer literal. After Stage 2 MinHash LSH dedup at Jaccard ≥ 0.85: SARD 53,666 raw → estimated 25,000–35,000 unique after near-dedup ExploitDB 1,000 raw → estimated 700–900 unique CVE/GitHub/OSV: minimal duplication within source; moderate cross-source overlap The pre_training_audit.py min_train_samples check (30,000) may FAIL on your first run. This is not a failure of collection. It is a failure of naive sample counting.

→ MITIGATION — Accurate dataset size projection and acceptance criteria revision Run Stage 2 dedup on SARD immediately after Stage 1. Get the real unique count before assuming 30K is achievable. Revised target: 25,000+ unique functions across all sources (not 30K raw samples). If unique count < 25,000 after all collectors: run Stage 3 CFA generation earlier — each CFA pair adds 1 unique sample. Update pre_training_audit.py: min_train_samples = 25,000 (not 30,000). Report honest unique counts in the paper — not raw sample counts. Reviewers will ask.

## R-06 — NVD API v1.0 Silently Returns Nothing

▲ RISK — Using old NVD endpoint produces zero samples with no error NVD API v1.0 was deprecated December 2023. As of 2024, it returns HTTP 404 or redirect. v2.0 response schema changed: result.CVE_Items[] → vulnerabilities[]. Old code written from tutorials or LLM memory will use the wrong URL and wrong field names. The collector will run for hours, produce zero index entries, and report no errors. You will only notice when you check cve_index.jsonl after 6 hours and find it empty.

→ MITIGATION — Hard-code v2.0 URL and add startup assertion Base URL must be: https://services.nvd.nist.gov/rest/json/cves/2.0 (note: 'cves' plural) Add startup assertion: assert '/2.0' in NVD_BASE_URL, 'Wrong NVD API version' After first 5 entries: assert len(entries) > 0, 'NVD returned zero results — check URL and API key' Pre-flight test (run before starting Phase 2): curl -H 'apiKey: $NVD_API_KEY' 'https://services.nvd.nist.gov/rest/json/cves/2.0?cweId=CWE-120&resultsPerPage=1' Verify: HTTP 200, 'totalResults' > 0 in JSON response.

# 4. High Risks — Full Detail

## R-07 — GitHub Token Missing or Expired

⚠ WARNING — Silent degradation: 60 requests per hour instead of 5000 A missing or expired GitHub token does not cause an error. It causes a rate limit of 60 req/hr. CVE Phase 2 (5000 commits to fetch): 5000 requests / 60 per hr = 83 hours. Expected: 5 hours. Repo Miner (torvalds/linux, 3000 security commits, ~300 pages to scan): 300 / 60 * 60 min = 5 hours per page scan alone. The collector will run, produce samples, and you will not notice the 16x slowdown until Day 4.

→ MITIGATION — Pre-flight rate limit check (mandatory before Day 3) curl -H 'Authorization: Bearer $GITHUB_TOKEN' https://api.github.com/rate_limit ¦ python3 -m json.tool ¦ grep '"limit"' If output shows 5000: token is valid. If 60: token is missing, wrong, or expired. Renew token at: github.com → Settings → Developer settings → Personal access tokens Required scopes: public_repo (read access to public repos). No write scopes needed. Add to BaseCollector __init__: call self._verify_github_token() which does the rate_limit check.

## R-08 — GitHub GraphQL Cursor Expiry

⚠ WARNING — Collection hangs permanently after cursor expires — common during rate limit sleeps When GitHub Advisory collector hits rate limit (< 400 points), it sleeps until reset. Reset can be 30–60 minutes away. During that sleep, the GraphQL cursor expires (~10 min). On resume: cursor is invalid → GraphQL returns error → unhandled → collector crashes. Checkpoint has last_cursor saved. On restart: uses stale cursor → error again → infinite crash loop. This is a production failure mode that will happen on every collection run that exceeds ~15 pages.

→ MITIGATION — Cursor expiry recovery with seen_advisory_ids fallback On GraphQL error containing 'cursor': clear cursor from checkpoint, restart from page 1. Maintain seen_advisory_ids set in checkpoint. On page 1 restart: skip already-seen GHSA IDs. Save cursor BEFORE processing page results (not after). If processing crashes, cursor is safe. Test this deliberately: after 3 pages, corrupt the cursor in checkpoint JSON. Verify recovery.

## R-09 — Repo Miner Keyword Filter Too Broad

⚠ WARNING — 'fix' in SECURITY_KEYWORDS = 880,000 commits to diff-fetch from torvalds/linux torvalds/linux has 1.1M commits. ~80% contain the word 'fix' in some form. At 5000 GitHub API calls/hour: 880,000 diff fetches = 176 hours. Just for Linux. Worse: that volume of requests will trigger GitHub's abuse detection — a 403 secondary rate limit. When that 403 hits, the collector will likely stall. Your GitHub token may be temporarily banned. The fix is simple (scored keywords) but must be implemented BEFORE running the Repo Miner.

→ MITIGATION — Scored keyword filter: require score >= 2 HIGH (score 3): 'cve-', 'security', 'vulnerability', 'vuln', 'exploit' — fetch diff immediately MED (score 2): 'overflow', 'buffer', 'heap', 'stack', 'use-after-free', 'injection', 'oob' — fetch diff LOW (score 1): 'fix', 'patch', 'bug', 'crash' — only fetch if score from other keywords also ≥ 1 EXCLUSIONS: skip if message contains 'typo', 'whitespace', 'formatting', 'style', 'doc', 'copyright' Net effect: Linux 880K candidates → ~15K. API budget: 3 hours for Linux. Acceptable. Test the filter on 100 real commit messages from openssl/openssl before running at scale.

## R-10 through R-15 — Summary

| Risk | Problem | Mitigation |
| --- | --- | --- |
| R-10: ExploitDB CWE guessing | No CWE in CSV → all ExploitDB samples fail validate_sample(). Without CWE inference, 0 samples collected. | Implement CWE_INFERENCE_MAP (keyword match on code + description). Skip samples with no match — do not guess. |
| R-11: Invalid ExploitDB mutations | ~30% of rule-based safe counterparts are syntactically invalid C. Stage 4 Joern will reject them. | Add gcc -fsyntax-only gate after each mutation. Only save pair if both original AND mutation compile clean. |
| R-12: CWE-416 / CWE-476 at 2% in SARD | Juliet has very few UAF and NULL-deref test cases. Model will not learn these patterns from SARD alone. | Run targeted CVE queries for CWE-416 and CWE-476 specifically. Target 500+ samples each from API sources. |
| R-13: Disk exhaustion mid-collection | Collector writes partial JSONL then crashes on RuntimeError. Partial lines corrupt the file. | BaseCollector raises at < 5GB free. Ensure 20GB free before starting. Check: df -h $STREAMGUARD_DATA_DIR |
| R-14: Checkpoint corruption on kill -9 | Hard kill between write and os.replace() leaves .tmp file. On restart, checkpoint is previous state (data replayed). | On startup: delete any *.tmp files in checkpoint dir. Add to BaseCollector.__init__: cleanup stale .tmp files. |
| R-15: HTTP 503 not retried | NVD returns 503 under load. Current safe_get() retries only on ConnectionError and Timeout. 503 → crash. | In safe_get(): add 503 handler with 30s sleep + jitter before retry. Same pattern as 429 Retry-After. |

# 5. Medium Risks — Summary

| Risk | Root Cause | Impact if Ignored | Fix |
| --- | --- | --- | --- |
| R-16: Short/full SHA mismatch | GitHub sometimes returns 7-char abbreviated SHAs in older API responses | Same CVE commit collected twice from CVE + OSV sources, wasting API budget | Normalize all SHAs to 40-char using /commits/{sha} lookup. Cache results. |
| R-17: GitHub 403 abuse detection | Synchronized burst retries after rate limit reset. No jitter. | Token temporarily banned. Collection pauses for hours or days. | Add random jitter (0.5–3.0s) to every retry. Handle 403 'secondary rate limit' with 120s sleep. |
| R-18: Hash load O(n) on restart | _load_seen_hashes() parses full JSONL on every __init__ | 30–60 second startup delay on restarts for 18K+ sample files | Persist seen hashes to {source}_hashes.txt. Fast load (strings, no JSON parse). |
| R-19: C macro expansion failures | tree-sitter can't parse macro-heavy C code. Functions using ALLOC_BUFFER() etc. are silently dropped. | ~5–10% of repo miner samples from kernel code are lost. More importantly, they land in *_failed.jsonl silently. | Log all tree-sitter failures to stage1_macro_failures.jsonl. Review top 20 failed patterns and add explicit expansions. |
| R-20: CWE inference wrong 15–25% | Keyword matching on commit message is imprecise. 'buffer' can mean CWE-120, 119, 121, or 122. | CWE-head training signal is noisy. per-CWE F1 degraded. | Store cwe_confidence field. Apply label smoothing on CWE head for low-confidence samples. Report honestly. |
| R-21: Label=0 dominates (58%+) | SARD has 1 bad() per file but 2–5 good() variants. MinHash removes near-dup good() but some remain. | Binary BCE loss biased toward safe predictions. FNR (missed vulnerabilities) will be high. | Monitor label balance in audit. If label=1 < 42%: down-sample label=0 or up-weight label=1 in loss function. |
| R-22: GitLab clone blocked by proxy | Corporate/VPN networks may block gitlab.com. Clone fails silently after 5 retries. | ExploitDB not collected. 800–1200 P0 samples missing. | Test git clone gitlab.com BEFORE starting Phase 2. Have fallback: download archive from GitLab directly. |
| R-23: OSV page token not persisted | OSV API uses page tokens for pagination. If checkpoint only saves entry count, restart re-fetches all pages. | 3–4 days of wasted API calls re-fetching already-seen advisories. | Checkpoint must save OSV page token explicitly: {last_page_token, entries_seen, samples_saved}. |

# 6. Data Quality — The Unvarnished Assessment

⚑ BLUNT REALITY — What you will actually have vs what you think you will have The plan says 33,600–52,300 samples. Here is the realistic breakdown after all quality gates: SARD raw: 53,666 → after Stage 1 + Stage 2 dedup: ~26,000–32,000 (Juliet near-dups removed) ExploitDB raw: 1,200 → after compile gate + dedup: ~500–800 (mutation failure rate ~35%) CVE raw: 4,000 → after Stage 1 C extraction: ~2,500–3,500 (not all diffs have clean functions) GitHub Adv raw: 3,000 → after C keyword filter + dedup: ~1,500–2,500 (many advisories are non-C) OSV raw: 1,500 → after SHA cross-dedup: ~800–1,200 (~30% overlap with CVE) Repo Miner raw:22,000 → after scored filter + C extraction: ~8,000–14,000 (C extraction quality varies) Realistic total BEFORE Stage 3 CFA: ~39,000–54,000 After Stage 3 CFA generation (×2–3 per vulnerable sample): ~80,000–140,000 total samples After final Stage 2 dedup on CFA samples: ~60,000–100,000 unique This is actually fine. The floor (39K pre-CFA, 60K post-CFA) exceeds the 30K minimum. The concern is CWE distribution, not total volume.

## 6.1 CWE Distribution Forecast

| CWE | SARD (now) | API Sources (est.) | Total Pre-CFA | Target | Status |
| --- | --- | --- | --- | --- | --- |
| CWE-120 | ~8,000 | ~1,500 | ~9,500 | 3,000 | ✓ Exceeded |
| CWE-121 | ~12,000 | ~800 | ~12,800 | 3,000 | ✓ Exceeded |
| CWE-122 | ~8,500 | ~1,200 | ~9,700 | 3,000 | ✓ Exceeded |
| CWE-134 | ~4,000 | ~600 | ~4,600 | 2,000 | ✓ OK |
| CWE-190 | ~6,000 | ~1,000 | ~7,000 | 2,000 | ✓ OK |
| CWE-416 | ~500 | ~1,200 | ~1,700 | 1,500 | ⚠ Marginal |
| CWE-476 | ~400 | ~800 | ~1,200 | 1,500 | ⚠ Below target |
| CWE-78 | ~1,500 | ~1,500 | ~3,000 | 1,200 | ✓ OK |
| CWE-89 | 0 | ~2,000 | ~2,000 | 2,000 | ⚠ API-dependent only |
| CWE-79 | 0 | ~500 | ~500 | 800 | ✗ Risk — very few C web CVEs |
| CWE-119 | 0 | ~1,500 | ~1,500 | 800 | ✓ OK if API works |
| CWE-125 | 0 | ~2,000 | ~2,000 | 800 | ✓ OK if Repo Miner runs |

⚠ WARNING — CWE-79 is the highest-risk CWE — plan for < 500 samples CWE-79 (Cross-Site Scripting in C web code) is genuinely rare. Most XSS is in PHP/JavaScript, not C. The only C sources are: CVE entries for nginx, Apache httpd, and embedded web servers. Realistic estimate: 300–600 unique CWE-79 C functions. Below the 800-sample target. Options: (1) Accept the limitation and note it honestly in the paper. (2) Broaden CWE-79 definition to include C template injection patterns. (3) Generate more CWE-79 synthetic samples via LLM (label as source='manual', flag in paper). Do NOT inflate the CWE-79 count by mis-labelling other CWEs as CWE-79.

## 6.2 Label Quality Assessment by Source

| Source | Label Assignment Method | Estimated Noise Rate | Confidence |
| --- | --- | --- | --- |
| SARD | NIST-labelled by name convention (bad/good). Verified by domain experts. | < 1% | VERY HIGH |
| ExploitDB | All label=1 (exploit = vulnerable by definition). Safe counterpart by rule-based mutation. | ~5% (mutation produces non-equivalent safe version) | HIGH for label=1, MEDIUM for label=0 |
| CVE | Before-commit = label=1, after-commit = label=0. Ground truth is the CVE fix. | ~10% (commit may fix unrelated issue; CWE mapping noisy) | MEDIUM |
| GitHub Advisory | Same as CVE. CWE from advisory when available, else inferred. | ~15% (many advisories have vague descriptions) | MEDIUM |
| OSV | Same as CVE. Generally high-quality commit data. | ~10% | MEDIUM-HIGH |
| Repo Miner | Security keyword filter on commit message. CWE inferred from code. | ~20% (keyword filter is imperfect; CWE inference error) | MEDIUM-LOW |

✔ VERDICT — Label noise at these levels is acceptable for the paper Label noise of 10–20% in the training set is common in vulnerability detection literature. SARD (your largest source) has < 1% noise. This anchors the overall noise level. Weighted average noise across all sources is approximately 8–12%. Within acceptable range. The CFA contrastive loss REDUCES the impact of label noise by forcing structural separation. Key: report noise estimates in the paper's dataset section. Do not hide them. Reviewers will ask 'how do you handle label noise?' — have a prepared answer.

# 7. Operational Risks — Reality of a 10-Day Collection Run

⚑ BLUNT REALITY — Background processes running for 10 days on a Windows dev machine will be interrupted. Laptop hibernate/sleep → network disconnect → API authentication expires → Python process killed. Windows Update will restart your machine. Your Python process will die. The checkpoint must survive. You will also make code changes during Phase 3 and forget that collectors are still running. Plan for interruptions. Do not plan for uninterrupted collection.

## 7.1 Interruption Resilience Requirements

| Scenario | Frequency | Checkpoint Behavior | Recovery Action |
| --- | --- | --- | --- |
| Laptop sleep/hibernate | Daily | Must survive. Checkpoint file preserved. | Re-run same command. Collector resumes from last page. |
| Windows Update restart | 1–2x over 10 days | Must survive. All JSONL intact. | Re-run. Dead processes restart from checkpoint. |
| kill -9 / Task Manager kill | Occasional | Checkpoint is previous-safe state. .tmp cleaned. | Re-run. Small rewind (last N samples replayed, dedup handles duplicates). |
| Network disconnect (mid-request) | Daily | tenacity retries 5 times. After 5: raises, checkpoint saved. | Re-run. Collector retries failed requests. |
| API token expiry (GitHub: 90 days) | Once | 401 raises ValueError. Collection stops. | Renew token. Re-run. |
| Disk full | Unpredictable | RuntimeError raised at < 5GB. Collector stops cleanly. | Free space. Re-run. |
| Python exception (unhandled bug) | Low but possible | Checkpoint saved at last save_checkpoint() call. | Fix bug. Re-run. |

## 7.2 Minimum Checkpoint Requirements

- Checkpoint writes MUST use os.replace() (atomic rename). Never overwrite directly.

- Checkpoint frequency: every 10 pages for API collectors, every 100 samples for local collectors.

- On startup: scan for *.tmp files in checkpoint dir and delete them (stale from previous hard kill).

- Checkpoint must contain enough state to skip ALL already-processed items on restart.

- JSONL files are append-only. The _seen_hashes set prevents re-saving duplicates on restart.

- Do NOT clear the JSONL output file on restart. Always append. Dedup handles replays.

## 7.3 Monitoring — Know What Your Collectors Are Doing

Running 4 collectors in background for 10 days without monitoring is asking for silent failure. Set up a daily check:

# Daily collection health check — run every morning

echo "=== COLLECTION STATUS ===" && date

for f in data/raw/**/*_samples.jsonl; do

count=$(wc -l < "$f")

modified=$(date -r "$f" "+%Y-%m-%d %H:%M")

echo "$f: $count samples (last modified: $modified)"

done

# Check if any collector has stalled (no new samples in 2+ hours)

# If last_modified > 2 hours ago AND collector process still running: investigate

# 8. Research Validity — What Reviewers Will Check

⚑ BLUNT REALITY — Conference reviewers for ISSTA/ICSE are experts in vulnerability datasets. They have read the ICSE 2025 paper about dataset quality problems. They will look for: (1) Contamination between train and test from shared CVE commits. (2) Inflated F1 from near-duplicate functions across splits. (3) CWE distribution collapse making multi-CWE claims unsubstantiated. (4) Synthetic data (SARD) not properly separated from real-world data (CVE) in evaluation. (5) Label noise estimates absent from the paper. If you cannot defend each of these in the paper, the paper will not be accepted.

## 8.1 Reviewer Questions and Your Answers

| Question Reviewer Will Ask | What You Must Show | Risk if Missing |
| --- | --- | --- |
| 'How did you prevent train/test leakage across 6 sources?' | Stage 7 commit_sha grouping. Stage 2 MinHash dedup. Post-audit CHECK 6 results. | Rejection: 'results may be inflated' |
| 'How did you validate your CWE labels?' | Tier 1-4 CWE confidence system. SARD labels from NIST. API labels with noise estimates. | Rejection: 'evaluation methodology unsound' |
| 'What is the duplication rate in your dataset?' | Stage 2 dedup reduction numbers (raw vs unique counts). MinHash threshold justification. | Rejection: 'dataset statistics unclear' |
| 'Why is CWE-79 only N=X samples?' | Honest statement: C web server CVEs are rare. This is a limitation, not a bug. | Acceptance with caveat, not rejection — IF disclosed proactively |
| 'How does SARD synthetic data affect real-world validity?' | Separate evaluation: SARD-only test set + real-world CVE test set. Show both metrics. | Major revision: 'results may not transfer to real code' |
| 'Can your results be reproduced?' | MLflow experiment IDs, fixed seed=42, dataset released on HuggingFace. | Rejection: 'insufficient reproducibility' |

## 8.2 Mandatory Ablation for Dataset Validity

In addition to the model ablations, you need a dataset ablation to answer reviewer question #5:

| Ablation | Train Split | Test Split | Purpose |
| --- | --- | --- | --- |
| A: SARD-only train | SARD functions only | SARD held-out | Baseline: what does SARD alone achieve? |
| B: Mixed train + SARD test | All sources | SARD test only | Does adding real-world data help on synthetic? |
| C: Mixed train + CVE test | All sources | CVE/GitHub/OSV only | Does it generalise to real-world CVEs? |
| D: Full train + real-world test (primary) | All sources (standard split) | Mixed held-out | Main result reported in paper |

If Config C F1 is dramatically lower than Config D: model is SARD-overfitted. This is a real result to report, not a failure to hide.

# 9. Risk Mitigation Implementation Tracker

Use this as a pre-flight checklist. All items must be checked before starting P2-S3, S4, S5, S6.

| Risk | Mitigation | Implemented In | Must Verify Before |
| --- | --- | --- | --- |
| R-01: Test set contamination | commit_sha grouping in Stage 7 split; cross-dedup in OSV + Repo Miner | P2-S5, P2-S6, Stage 7 | Training. Check audit R-01. |
| R-02: CWE coverage collapse | Daily CWE count monitoring; targeted supplementation if < 500 | P2-S7 audit | Starting Phase 3 Stage 3. |
| R-03: Broken CFA pairs | finalize_pairs() in BaseCollector; audit CHECK 5; Stage 2 re-check | P2-S1 (BaseCollector) | Any training run. |
| R-04: Label noise | CWE confidence tiers; label smoothing in training | P2-S3, S4, S5, S6 | Paper submission. |
| R-05: Duplicate inflation | Stage 2 MinHash LSH; honest unique-count reporting | Stage 2 (existing) | Reporting sample counts. |
| R-06: NVD v1.0 URL | Hard-coded v2.0 URL; startup assertion; pre-flight curl test | P2-S3 | Starting P2-S3. |
| R-07: GitHub token | Pre-flight rate_limit check; assertion in collector __init__ | P2-S3, S4, S5, S6 | Day 3 start. |
| R-08: GraphQL cursor expiry | seen_advisory_ids fallback; cursor saved BEFORE processing page | P2-S4 | Starting P2-S4. |
| R-09: Repo Miner keyword overload | Scored keyword filter (score >= 2); exclusion list | P2-S6 | Starting P2-S6. |
| R-10: ExploitDB CWE guessing | CWE_INFERENCE_MAP keyword scoring; skip no-match samples | P2-S2 | Starting P2-S2. |
| R-11: Invalid C mutations | gcc -fsyntax-only gate; discard invalid mutation | P2-S2 | Starting P2-S2. |
| R-12: CWE-416/476 shortage | Targeted CVE queries for these CWEs; monitor in P2-S7 | P2-S3 + P2-S7 | Starting Phase 3 Stage 3. |
| R-13: Disk exhaustion | 5GB threshold in BaseCollector; check all relevant volumes | P2-S1 (BaseCollector) | Starting Phase 2. |
| R-14: Checkpoint corruption | Startup .tmp file cleanup in BaseCollector.__init__ | P2-S1 (BaseCollector) | Starting Phase 2. |
| R-15: HTTP 503 not retried | 503 handler in safe_get() with 30s sleep | P2-S1 (BaseCollector) | Starting Phase 2. |
| R-16: Short SHA mismatch | SHA normalization in all API collectors; cache | P2-S3, S5, S6 | Starting P2-S5. |
| R-17: GitHub 403 abuse | jitter_sleep() in BaseCollector; 403 secondary handler | P2-S1 (BaseCollector) | Starting Phase 2. |
| R-18: Hash load O(n) | _hashes.txt fast path in BaseCollector | P2-S1 (BaseCollector) | Starting Phase 2. |
| R-19: C macro failures | Log tree-sitter failures; review top patterns | Stage 1 (existing) | Starting Phase 3. |
| R-20: CWE inference noise | Confidence field; smoothing during training | P2-S3 through S6 | Paper submission. |
| R-21: Label imbalance | Monitor ratio; weight label=1 in loss if < 42% | P2-S7 audit | Starting training. |
| R-22: GitLab clone blocked | Test git clone BEFORE Day 2; have archive fallback | Pre-Phase 2 setup | Day 2. |
| R-23: OSV page token | Save page_token in checkpoint | P2-S5 | Starting P2-S5. |
| R-24: Windows path with (1) | Always pass parent dir to SARD collector | P2-S2 prompt | Day 2. |
| R-25: chardet latin-1 corruption | Log encoding fallbacks; spot-check affected samples | Stage 1 (existing) | Starting Phase 3. |
| R-26: Linux Repo Miner runtime | Start last; checkpoint every 10 pages | P2-S6 | Starting P2-S6. |
| R-27: MLflow not running | Log to CSV fallback if MLflow unavailable | train.py | Starting Phase 4. |

# 10. Go / No-Go Decision Criteria

These are the hard gates. If any condition is not met, do NOT proceed to the next phase.

| Gate | Condition | Check Command | If FAIL |
| --- | --- | --- | --- |
| BEFORE starting P2-S3/S4/S5/S6 | GitHub token returns 5000 req/hr | curl -H 'Authorization: Bearer $GITHUB_TOKEN' https://api.github.com/rate_limit ¦ grep limit | Renew token. Do not start API collectors. |
| BEFORE starting P2-S3 | NVD API v2.0 returns results | curl -H 'apiKey: $NVD_API_KEY' '...nvd.nist.gov/.../cves/2.0?cweId=CWE-120&resultsPerPage=1' | Check API key. Verify v2.0 URL. Do not start CVE collector. |
| BEFORE starting P2-S3 | Disk free > 20GB on data volume | df -h $STREAMGUARD_DATA_DIR | Free disk space first. |
| BEFORE starting P2-S6 | Repo Miner keyword filter returns score >= 2 for real security commits | Test on 20 real openssl commit messages manually | Adjust scoring. Do not mine at scale with broken filter. |
| BEFORE Phase 3 | P2-S7 audit: all 10 checks PASS | python3 audit_phase2.py | Fix all FAILs. Re-run audit. |
| BEFORE Phase 3 | Zero broken CFA pairs in merged JSONL | Audit CHECK 5 | Call finalize_pairs() on each collector output. Re-run audit. |
| BEFORE Phase 3 | All VALID_CWE types have >= 200 samples | Audit CHECK 3 | Run targeted collection for underrepresented CWEs. |
| BEFORE training | Zero commit SHA overlap between train and test splits | Stage 7 assertion | Re-run Stage 7 split with correct grouping logic. |
| BEFORE paper submission | SARD-only test set evaluations complete (dataset ablation) | Run ablation Configs A–D from Section 8.2 | Cannot submit without dataset validity ablation. |

✔ VERDICT — If you implement every mitigation in this document You will have a dataset that is defensible in a top-venue paper. You will be able to answer every reviewer question about data quality. Your F1 numbers will be honest and reproducible. The per-CWE claims will be substantiated for 10 of 12 CWEs (CWE-79 and possibly CWE-476 will require a footnote). Shortcuts will not save time. They will cost time — when you discover a data problem after 3 days of training and have to restart. Every checkpoint in this document exists because someone, somewhere, skipped it and paid the price.

Phase 2 Risk Analysis | StreamGuard v1.0 | March 2026